NIGERIA EXTRACTIVE INDUSTRIES TRANSPARENCY INITIATIVE (NEITI)

MONITORING AND EVALUATION REPORT, 2023

BY: THE MONITORING AND EVALUATION UNIT, POLICY, PLANNING AND STRATEGY DEPARTMENT

MAY, 2024

# LIST OF ACRONYMS & ABBREVIATIONS

APR	Annual Progressive Report

CT	Contract Transparency

E.I	Extractive Industries

EITI	Extractive Industries Transparency Initiative

EOI	Expression of Interest

FAAC	Federation Account Allocation Committee

FASD	Fiscal Allocation and Statutory Disbursement Audit FIRS	Federal Inland Revenue Service

GIZ	Deutsche Gesellschaft Fur Internationale Zusammenarbeit ICT	Information and Communications Technology

IMTT	Inter Ministerial Task Team

IPPIS		Implementing Integrated Personnel Payroll Information System IPSAS	International Public Sector Accounting Standards

M&E	Monitoring & Evaluation

MLFA	Modified Logical Framework Analysis

MSG	Multi-stakeholders Group

NAMS	NEITI Data Automation System

NEITI		Nigeria Extractive Industries Transparency Initiative NSWG	National Stakeholders Working Group

O&G	Oil & Gas

OAGF	Office of the Accountant General of the Federation. PB	Policy Briefs

PIA	Petroleum Industry Act

SM	Solid Minerals

TUGAR	Technical Unit on Government and Anti-Corruption Reforms UNCAC	United Nations Convention Against Corruption

TABLE OF CONTENT

  - Introduction

  - NEITI 2022-2026 strategic plan objectives.

  - National Priorities

  - International Priorities

  - EITI Strategic Priorities

  - 2023 Workplan Objectives

  - 2023 Workplan Monitoring & Evaluation Objectives

  - Methodology

  - 2023 Workplan Performance Analysis

  - Five years Workplan Performance Trend Analysis

  - Workplan Implementation Status Table

  - Findings

  - Challenges

  - Recommendations

# EXECUTIVE SUMMARY

This monitoring and evaluation (M&E) report for the 2023 Nigeria Extractive Industries Transparency Initiative (NEITI) country work plan is the second series in the implementation of the NEITI 2022-2026 Strategic Plan. The M&E exercise tracks and documents performance and progress recorded in implementing the 2023 NEITI Country Work Plan.

The work plan was designed and implemented to achieve the strategic plan objectives, deepen implementation of the global Extractive Industries Transparency Initiative (EITI) in Nigeria, sustain the ongoing reforms in the oil, gas, and mining sectors, and address the country’s national priorities.

The monitoring and evaluation exercise was carried out in compliance with Requirement 1.5 of the EITI 2023 Standard. The exercise was conducted using the NEITI’s monitoring and evaluation framework.

From the assessment, the 2023 NEITI work plan implementation indicates that 58.9% of the programs and activities in the plan were completed, 21.9% were in progress, and 19.2% were not started at the end of December 2023. This represent a decline in performance when compared with work plan implementation performances in previous years. The performance in 2019, 2020, and 2021 shows that 70%; 73%, 71% of programs and activities in the work plan were respectively completed. Although, there was a 4.2% improvement in completion in the implementation of the work plan from 54.8% in 2022 to 58.9% in 2023.

The decline in the 2023 workplan implementation performance against previous years can be attributed to unrealistic programs and activities in the work plan; problems of non-adherence to implementation of the work plan; failure to conduct a mid-year review of the work plan as at when due; inability to secure management’s approval for some programs and activities in the workplan; and repetition of activities among other factors.

The exercise also reveals that while implementation of the NEITI’s strategic objective 2, which deals with sustaining extractive sector reporting, regular industry audits, disclosure, etc. recorded 60.7% of its activities as completed, the implementation of strategic objective 1, which deals with strengthening extractive sector governance and reforms, policy research, strategic stakeholder engagement, communication etc. recorded just 50.6% of its activities completed. The implication of this is that it may be difficult to deliver on the accountability mandate of NEITI if this trend continues.

The report recommend that management should ensure strict adherence to the program and activities outlined in the work plan; a prompt mid-year review of the work plan needs to be taken more seriously. Besides, leadership approvals release of funds for programs and activities should be consistent with items in the work plan.

The process of work plan development and implementation needs to be more robust and stakeholder-inclusive. Equal and adequate attention should be paid to the implementation of programs and activities across all the NEITI’s three strategic objectives. Capacity building for monitoring and evaluation of staff/focal persons across all the departments in the organization is also recommended.

# INTRODUCTION

The 2023 work plan is the second series in the implementation of the NEITI 2022-2026 strategic plan. The activities and programs in the work plan were designed and implemented to achieve the strategic plan objectives, namely: to strengthen extractive sector governance and reforms through policy research, strategic stakeholder engagement, communication, and inter-agency collaboration; to sustain extractive sector reporting and relevance by focusing on national and international priorities; and to achieve operational excellence in implementing the NEITI mandate through professionalism, innovation, use of technology, resource management, and capacity building.

The 2023 work plan outlined programmes and activities, timelines as  well as performance indicators to guide its implementation in line NEITI strategic objectives within period. The work plan was anchored on requirement of the global EITI while reflecting national priorities. The plan was also designed to address emerging global issues in the EITI process and improving revenue for the government.

The program and activities outlined in the 2023 work plan were broader in scope and tailored to meet national and international commitments and timelines on EITI validation. This monitoring and evaluation exercise and reporting is conducted using NEITI’s monitoring and evaluation framework and in compliance with Requirement 1.5 of the 2023 EITI Standard.

# NEITI 2022-2026 STRATEGIC OBJECTIVES:

Strategic Objective 1: Strengthen extractive sector governance and reforms through policy research, strategic stakeholder engagement, communication, and inter-agency collaboration.

Strategic Objective 2: Sustain extractive sector reporting and relevance by focusing on national and international priorities

Strategic Objective 3: Achieve operational excellence in implementing the NEITI mandate through professionalism, innovation, use of technology, resource management, and capacity building.

# NEITI Vision

A Nigeria whose extractive sector is transparent, accountable, and beneficial to all.

# NEITI Mission

To institutionalize accountability mechanisms and processes to instil a culture of transparency

and participation in Nigeria’s extractive sector for the benefit of all.

# NEITI 2023 WORK PLAN OBJECTIVES

The 2023 NEITI work plan was designed to consolidate and deepen EITI implementation in Nigeria by ensuring transparency and accountability in the application, reporting, and management of extractive revenues for the public good. The specific objectives are to

- Increase public enlightenment of the EITI process, and emerging global trends and enhance impact

and relevance in Nigeria’s extractive sector.

- Broaden & deepen Stakeholder Engagement in the EITI Process.

- Timely disclosure of information and data across the industry value chain

- Conduct Research and Studies to Strengthen Policy Reforms in the E.I Sector

- Facilitate public sector accountability through monitoring and evaluation of governance initiatives, internal control, and data base coordination.

- Improve reporting on current and emerging issues through comprehensive data sources mapping & Improve reporting on current and emerging issues through comprehensive data sources mapping

- Improve reporting through automation of data gathering process

8. Enhance relevance of NEITI’s work by focusing on National and international Priorities

- To maintain high quality accounting standards in the presentation of financial statement reporting

- Achieve operational Excellence in Implementation of NEITI mandate

# NATIONAL PRIORITIES:

The national priorities of the Federal Government of Nigeria itemized below as contained in the Medium-Term National Development Plan 2022- 2025 were incorporated in the plan.

- Build a thriving and sustainable economy

- Attain energy sufficiency in power and petroleum products.

- Build a system to fight corruption, improve governance, and create national cohesion.

# INTERNATIONAL PRIORITIES:

The International priorities itemized below as contained in the 2019 EITI standard were considered and incorporated into the plan.

- Commodity Trading Transparency

- Environmental Disclosures

- Opening Extractives

- Gender Reporting

- Energy Transition

- Beneficial Ownership Disclosure

# WORK PLAN MONITORING & EVALUATION OBJECTIVE

The objective of the monitoring and evaluation exercise and reporting is to track and document performance and progress recorded in the implementation of the work plan, to help achieve the NEITI’s strategic plan objectives, deepen implementation of the Extractive Industries Transparency Initiative (EITI) in Nigeria, sustain the ongoing reforms in the oil, gas, and mining sectors and address the country’s national priorities while ensuring compliance with requirement

1.5 of the EITI 2023 standard.

# METHODOLOGY:

The monitoring and evaluation exercise for the NEITI 2022 work plan adopted a Modified Logical Framework Analysis (MLFA). The exercise involved designing of monitoring and evaluation data collection template which was populated by various NEITI departments/units implementing different aspects of the work plan based on the status of activities and programs in the work plan as of December 2023. The data and information in the populated template were therefore collated, analysed, and evaluated by NEITI’s Planning, Monitoring, and Evaluation unit. This forms the basis for the content of this report.

The program and activities in the work plan were analysed and evaluated using the following approach:

1. Program/activities were measured based on status (i.e. not started, in progress, or completed) as of December 2023.

- Programs/activities are considered “Completed” when they deliver expected outcomes by December 2023.

- Programs/activities are considered ‘In Progress’ where there is clear evidence(s) that such programs and activities have commenced within the reporting period.

- Programmes/activities are considered not ‘started ‘where it has not commenced as of the end of December 2023.

- A simple average of programs/activities was taken to arrive at a percentage analysis of the work plan implementation performance. This is done by dividing the number of programs/activities status by the total number of the year’s activities multiplied by a hundred.

# PERFORMANCE EVALUATION BY STRATEGIC OBJECTIVES

Strategic Objective 1: An evaluation of activities under this objective indicates that 50.6% of the planned activities were completed, 15.3% are in progress and 34.1% could not start at the end of the reporting year.

Strategic Objective 2: An evaluation of activities under this objective shows that 60.7% of the planned activities were completed, 23.2% were in progress and 16.1% have not started as of the end of December 2022.

Strategic Objective 3: An evaluation of activities under this objective indicates that 66.3% of the planned activities were completed, 27.7% were in progress, and 6.0% were not started as of the end of the year.

# Work Plan Performance by Strategic Objectives Table

The analysis of work plan implementation by strategic objectives is represented in the table and chart below.

# Table 1: Performance by Strategic Objectives table (%)

| Strategic Objectives | 1 | 2 | 3 |
| --- | --- | --- | --- |
|  | Strengthen extractive sector governance and reforms through policy research, strategic stakeholder engagement, communication, and inter- agency collaboration | Sustain extractive sector reporting and relevance by focusing on national and international priorities | Achieve operational excellence in implementing the NEITI mandate through professionalism, innovation, use of technology, resource management, and capacity building |
| Completed | 50.6% | 60.7% | 66.3% |
| In Progress | 15.3% | 23.2% | 27.7% |
| Not Started | 34.1% | 16.1% | 6.0% |

OBJECTIVES PERFORMANCE CHART

Completed

In Progress

Not Started

OBJECTIVE 1

OBJECTIVE 2

OBJECTIVE 3

%

0.7%

66.3%

Figure 1: Performance by Strategic Objective

| 50.6 % |  |  |  |  |  |  | 6 |  |  |  |  |  |  |  |  | 27.7% |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  |  | 23.2% |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 34.1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 15.3% |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 6.0% |  |  |
|  |  |  |  |  |  |  |  |  |  |  | 1 |  |  |  |  |  |  |  |  |  |

6.1%

OVERALL WORK PLAN IMPLEMENTATION/PERFORMANCE:

The assessment of the overall performance in the implementation of the 2023 NEITI work plan indicates that 58.9% of the programs and activities in the 2023 work plan were completed, 21.9%

were in progress, while 19.2% were not started at the end of December 2023. The assessment is represented in the table, chart, and graph below:

# Table 2: Summary of Overall Work Plan Implementation/Performance:

| Strategic Objectives | Completed | In Progress | Not Started | Total |
| --- | --- | --- | --- | --- |
| Objective 1 | 43 | 13 | 29 | 85 |
| Objective 2 | 34 | 13 | 09 | 56 |
| Objective 3 | 55 | 23 | 05 | 83 |
| Overall Total | 132 | 49 | 43 | 224 |
| % Average | 58.9% | 21.9% | 19.2% | 100% |

Figure 2: Performance assessment graph:

ACTIVITIES PERFORMANCE CHART

43

49

132

Completed

In Progress

Not Started

  - FIVE YEARS TREND ANALYSIS OF WORK PLANS PERFORMANCES:

The five-year trend analysis shows that the NEITI 2023 work plan implementation recorded a performance decline when compared with work plan performances in previous years. The work plan performance assessment in 2023 shows that 58.9% of programs and activities in the plan were completed, while 70%; 73%, 71% and 54.8% of programs and activities in the work plan for years 2019, 2020, 2021 and 2022 respectively were completed. The performance decline in 2023 can be attributed to unrealistic planned programs and activities; non-adherence to implementation of the programs and activities in the work plan; the failure to conduct a mid-year review of the work plan; inability to secure management’s approval for some programmes and activities; and repetition of activities among other factors.

# Table 3: Performance Trend Analysis (5 years)

| Year | Completed % | In Progress % | Not Started % |
| --- | --- | --- | --- |
| 2019 | 70 | 18 | 12 |
| 2020 | 73 | 23 | 4 |
| 2021 | 71 | 23 | 6 |
| 2022 | 54.8 | 21.4 | 23.8 |
| 2023 | 58.9 | 21.9 | 19.2 |

# Figure 4: Five Years Performance Trend Analysis

FIVE YEARS PERFORMANCE TREND ANALYSIS

80

70

60

50

40

30

20

10

0

2019

2020

Completed %

2021

In Progress %

2022

Not Started %

2023

| S/N | ACTIVITY | OBJECTIVE | START/END MONTH | STATUS OF ACTIVITY (ITEMS REMOVED FROM WP SHOULD BE MARKED AS NOT STARTED.) |  |  | OUTCOME |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | INCLUDED/NOT INCLUDED IN THE WORK PLAN | STRATEGIC | INCLUDED/ NOT INCLUDED IN THE WORK PLAN | NOT STARTED | IN PROGRESS | COMPLETED | AS STATED IN THE WORK PLAN |
|  | STAKEHOLDERS ENGAGEGEMENT PLAN | Strengthen extractive sector governance and reforms through policy research, strategic stakeholder engagement, communication, and inter-communication, and interagency collaboration. |  |  |  |  |  |
| 1 | Development of stakeholders’ engagement framework |  | Jan – Feb |  | X |  | Improved public understanding of the NEITI process |
| 2 | Development of a framework for social media engagement |  | Jan - Feb | X |  |  | Improved public understanding of the NEITI process |
| 3 | Review and development of NEITI stakeholders' map |  | Jan - Feb | X |  |  | Improved public understanding of the NEITI process |
| 4 | Stakeholders Engagement on NEITI country workplan & 2022 Annual Progress Report (APR) |  |  |  |  | X | Improved public understanding of the NEITI process |
| 5 | Stakeholders' engagement on finding and recommendations contained in the NEITI Reports and research documents. |  | Mar – Nov |  | X |  | Improved public understanding of the NEITI process |
| 6 | Convening of the IMTT |  | May – Dec |  |  | X | Improved public understanding of the NEITI process |
| 7 | Conduct Quarterly press briefings on NEITI activities and industry trends. |  | Jan – Dec |  |  | X | Improved public understanding of the NEITI process |
| 8 | Conduct capacity building workshop for NEITI stakeholders in the extractive sector- Govt entities; CSOs; Media; Companies. |  | May-Dec |  |  | X | Improved public understanding of the NEITI process |
| 9 | Support setting up Sub National Offices |  |  |  |  | X |  |

2.0 NEITI 2022 WORK PLAN IMPLEMENTATION STATUS TABLE Table 4

STRATEGIC OBJECTIVE 1

| 10 | Engagement with Governors Forum |  | Jan – Dec |  | X |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 11 | Engagement with ALGON |  | Jan – Dec | X |  |  |  |
| 12 | Develop framework for engagement on Energy Transition |  | June - July | X |  |  | Framework adoption and deployment by stakeholders |
| 13 | Develop contract transparency template for solid minerals sector |  | Feb – Apr | X |  |  | Template adopted and utilized by relevant stakeholders |
| 14 | Company forum engagement on energy transition |  | August | X |  |  | Relevant data disclosure and process change by O&G companies |
| 15 | Engagement with regulators on energy transition |  | July | X |  |  | Adoption of guidelines by relevant stakeholders |
| 16 | Staff, CSO and media workshop on Energy Transition |  | October | X |  |  | Engagements and dissemination activities by media and CSOs on ET Utilization of contract disclosure data by Media and CSOs for analysis, engagement and advocacy |
| 17 | Policy roundtable on Nigeria's SWF |  | June | X |  |  |  |
| 18 | Workshop with mining stakeholders on contract transparency template |  | May | X |  |  | Deployment of Transparency Template by mining regulators |
| 19 | Staff, CSO and Media workshop on contract transparency |  | October |  | X |  |  |
| 20 | Validation workshop on solid minerals study |  | September | X |  |  | Review of solid minerals policies and practices by stakeholders; use of report findings for analysis and advocacy by CSO and media |

| 21 | Stakeholders' conference on solid minerals reforms |  | October | X |  |  | Review of solid minerals policies and practices by stakeholders; use of report findings for analysis and advocacy by CSO and media |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 22 | Engagement with stakeholders on 2022 Annual Progress Report |  |  |  |  | X |  |
| 23 | Stakeholder engagement on development of 2024 workplan |  |  | X |  |  |  |
| 24 | Engagement with supreme Audit Institutions in Nigeria |  |  | X |  |  |  |
|  | COMMUNICATIONS & OUTREACH PLAN |  |  |  |  |  |  |
| 25 | Printing and distribution of NEITI Industry Report |  | Jan – Dec |  |  | X |  |
| 26 | Simplification of the 2021 NEITI Industry Audit reports -2021 |  | February |  |  | X |  |
| 27 | Public presentation of 2021 NEITI Industry Audit reports |  | February |  |  | X |  |
| 28 | Review all existing NEITI publications and develop new IEC materials/Fact sheets etc. |  | Mar - Nov |  |  | X |  |
| 29 | Conduct capacity building workshop on NEITI process for Clerks of the relevant Committee of the NASS |  | June - Sept | X |  |  |  |
| 30 | Conduct regular radio programs to educate & inform the public about the NEITI process and EI issues |  | Jan - Dec |  |  | X |  |
| 31 | Update and content management of the NEITI website |  |  |  |  | X |  |
| 32 | Publish NEITI industry reports in an open data format and circulate them |  |  |  |  | X |  |
| 33 | Production of the NEITI Quarterly Reviews |  | Mar - Dec |  |  | X |  |
| 34 | Publishing of the NEITI Quarterly Reviews |  |  |  |  | X |  |
| 35 | Deploy innovative and new digital media communication technologies to boost NEITI communication efforts and reach |  | Jan - Dec |  |  | X |  |
| 36 | Consumables for DI machine and other digital equipment |  | January |  |  | X |  |
|  | NSWG GOVERNANCE, RESEARCH AND POLICY REFORMS PLAN |  |  |  |  |  |  |
| 37 | Improving efficiency and productivity of both the downstream and upstream sector |  | October | X |  |  | Use of report for analysis and for decision making by stakeholders |

| 38 | Effective and efficient metering and measurement of crude oil |  | September | X | Use of report for analysis and for decision making by stakeholders |
| --- | --- | --- | --- | --- | --- |
| 39 | Curbing oil theft and pipeline vandalism |  | Feb-Apr | X | Use of report for analysis and for decision making by stakeholders (Report submitted to the Presidential Committee o Crude Oil Theft) |
| 40 | Deploying EITI framework in implementation of PIA |  | Jan-Mar | X | Use of report for analysis and for decision making by stakeholders |
| 41 | Alternatives to fuel subsidy |  | Feb-Apr | X | Use of report for analysis and for decision making by stakeholders (Policy Advisory submitted to the Minister of Finance/Fede ral Government of Nigeria) |
| 42 | Corruption risk assessment in the extractive sector |  | Mar-Dec | X | Use of report for analysis and for decision making by stakeholders |
| 43 | Strategies for optimizing revenue diversification |  | July-Sept | X | Use of report for analysis and for decision making by stakeholders (Policy Advisory submitted to the Minister of Finance/Fede ral Government of Nigeria) |

n

- Improving revenue generation/gap analysis, unlocking the leakages

- Assessing operational impacts of energy transition on the oil and gas sector

- Review of policy and management of Nigeria's sovereign wealth fund and the adequacy of the future generations fund

- Review of institutional framework of the solid minerals sector

- Review of benefit sharing and social contribution policies and practices in the solid minerals sector

Sept-Dec	X	Use of report

for analysis and for decision making by stakeholders

Jan-Mar	X	Use of report

for analysis and for decision making by stakeholders

Apr-May	X	Use of report

for analysis and for decision making by stakeholders

Feb-May	X	Use of report

for analysis and for decision making by stakeholders

Mar-Jun	X	Use of report

for analysis and for decision making by stakeholders

- Preparation of 2022 EITI Annual	X

Progress Report

- Development of 2024 Annual	X

Country Workplan

- Monitoring and Evaluation activities	X

- Studies on the Implication of Frontier Basins Exploration INTER AGENCY CORDINATION AND COLLABORATION PLAN

- Research Studies of Anti-Corruption and Governance Initiatives

- Follow up activities on TI-CPI

X

Q1-Q4	X	Updated database on anti- corruption initiatives

Q1-Q4	X	Better

analysis and the implementation of

implementatio

Executive Order 1

- Follow up activities on TUGAR Ethics Survey and Gap Analysis

n of Executive Order 1

Q1-Q4	X	Better Implementati on of the Code of Conduct for Public Officers through effective utilization of

|  |  |  |  |  | the Ethics Manual |
| --- | --- | --- | --- | --- | --- |
| 56 | Development of a platform for updating anti-corruption database |  | Q1-Q4 | X | Availability of data in an easily retrievable format for reporting towards sustainable development |
| 57 | Implementation of the National Anti-Corruption Strategy (Monitoring and Evaluation) |  | Q1-Q4 | X | Better implementati n of the NACS |
| 58 | Corruption Risk Assessment in the Nigerian Ports - Implementation of Integrity Plan |  | Q1-Q4 | X | Systems and structures within the sector strengthened |
| 59 | Corruption Risk Assessment in the Extractive Sector |  | Q1-Q4 | X | Systems and structures within the sector strengthened |
| 60 | Review of Nigeria's Implementation of the UNCAC - implementation of the Remediation Plan for the 1st & 2nd review Cycles |  | Q1-Q4 | X | Anti- corruption structures strengthened and better compliance with treaty obligations |
| 61 | Ninth Session of the Conference of State Parties to the United Nations Convention against Corruption (UNCAC) |  | Q4 | X |  |
| 62 | Coordination of the Anti- Corruption Agencies on the platform of the IATT |  | Q1-Q4 | X | Increased cooperation and synergy among the anti- corruption agencies |
| 63 | Joint Commemoration of the International Anti-Corruption Day |  | Q4 | X | Increased cooperation, collaboration and synergy among the anti- corruption agencies |
| 64 | Joint Commemoration of the African Anti-Corruption Day |  | Q3 | X |  |

o

| 65 | Use of stakeholder engagement to propagate the EITI to the public space. |  | Jan – Dec |  |  | X | Increase public enlightenmen of the EITI process and emerging global trends and enhance impact and relevance in Nigeria’s Extractive sector |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 66 | Coordinated Public Presentation of Oil, gas, Mining and FASD Industry Reports |  | Aug – Nov |  |  | X | Increase public enlightenmen of the EITI process and emerging global trends and enhance impact and relevance in Nigeria’s Extractive sector. |
| 67 | Visit of SGF to NEITI House for the launch of NEITI 2022-2026 Strategic plan |  | May 2023 |  |  | X |  |
| 68 | Media Briefings and Press Statements |  | Jan – Dec |  |  | X |  |
| 69 | NUPRC signing of seven new regulations |  | May 2023 |  |  | X |  |
| 70 | Departmental knowledge sharing session with the Executive Secretary |  | April 2023 |  |  | X |  |
| 71 | Supported coordination of Stakeholders validation workshop on 2022 APR |  | June |  |  | X |  |
| 72 | Collaboration with Women in Mining |  | June |  |  | X |  |
| 73 | Participated at the African Anti- Corruption Day 2023 |  | July |  |  | X |  |
| 74 | SERAP (Socio Economic Rights and Accountability Project) Interactive session and press briefing on promoting transparency and accountability in the use of public funds in Nigeria with focus on Niger Delta |  | Sept 2023 |  |  | X |  |
| 75 | Training on sharpening communication skills |  | Oct 2023 |  |  | X |  |
| 76 | Training on speech and report writing |  | Oct 2023 |  |  | X |  |
| 77 | SITEI Conference by CSR-in Action |  |  |  |  | X |  |
| 78 | ANEEJ AFRICA Network for environment and economic justice- National Dialogue |  |  |  |  | X |  |
| 79 | Policy Advisory to the new Government on Extractive Sector reforms |  | June – July 2023 |  |  | X |  |

e sector reporting

N

| 80 | FAAC Review for the period Jan 2022 to June 2023 (18 months). |  |  |  |  | June 2022 – Jan 2023 |  |  |  | X |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 81 | Updating the integrity plan in the MDG Related MDAs |  |  |  |  |  |  | X |  |  |  |
| 82 | Inter-Agency coordination and collaboration. Coordination of the Anti- Corruption Agencies on the platform of the IATT |  |  |  |  |  |  |  | X |  |  |
| 82 | Tenth Session of the Conference of States Parties to the United Nations Convention against Corruption |  |  |  |  |  |  |  |  | X |  |
| 84 | Corruption Risk Assessment in the Nigerian Law Reform Commission |  |  |  |  | Q1 |  |  |  | X |  |
| 85 | Tenth Session of the Conference of States Parties to the United Nations Convention against Corruption |  |  |  |  |  |  |  | X |  |  |
| 29 |  | 13 | 43 |  |  |  |  |  |  |  |  |

| S/N | ACTIVITY | OBJECTIVE | START/END MONTH | STATUS OF ACTIVITY (ITEMS REMOVED FROM WP SHOULD BE MARKED AS NOT STARTED.) |  |  | OUTCOME |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | INCLUDED/NOT INCLUDED IN THE WORK PLAN | STRATEGIC | INCLUDED/ NOT INCLUDED IN THE WORK PLAN | NOT STARTED | IN PROGRESS | COMPLETED | AS STATED IN THE WORK PLA |
|  | CONDUCT SCOPING STUDY OF ALL SECTOR REPORTS | and relevance by focusing on national and international priorities |  |  |  |  |  |
| 1 | Scoping study for Oil and Gas Sector |  | Apr-23 |  |  | X | Improved Data, Evidence Source and Quality of Audit report |
| 2 | Scoping study for the Solid Mineral Sector |  | Apr-23 |  |  | X | Improved Data, Evidence Source and Quality of Audit report |
| 3 | Scoping study for FASD |  | Apr-23 |  |  | X | Improved Data, Evidence Source and Quality of Audit report |
| 4 | Oil and gas Reconciliation Report 2022 |  | Sep-23 |  |  | X | Oil & Gas Industry Report |
| 5 | O &G Template Workshop |  | Jan-23 |  |  | X | Improved Data |
| 6 | Data collection exercise |  | Jan-23 |  |  | X | Data Collected |
| 7 | O&G Reconciliation and Validation exercise |  | Jan-23 |  |  | X | Reconciled & Validated Data |

STRATEGIC OBJECTIVE 2

| 8 | Solid Minerals reconciliation report 2022 |  | Feb-23 | X | SM Industry Report |
| --- | --- | --- | --- | --- | --- |
| 9 | SM Template Workshop for 3 locations |  | Feb-23 | X | Improved Data |
| 10 | Data collection |  | Feb-23 | X | Reviewed templates |
| 11 | SM Reconciliation and Validation meetings in 3 geopolitical zones |  | Aug-23 | X | Final SM report |
| 12 | SM stakeholders' engagement with Government Agencies |  | Mar-23 | X | Final SM report |
| 13 | FASD reconciliation report 2022 |  | Mar- May | X | FASD Report |
| 14 | Sensitization workshops to cover scope expansion |  | Jul-23 | X | Improved Data |
| 15 | FASD Template Workshop |  |  | X |  |
| 16 | Data collection |  | Sep-23 | X | FASD Report |
| 17 | Reconciliation and Validation meeting |  | Mar-23 | X | Validated & Reconciled Data |
| 18 | Data Automation Mgt System NAMS upgrade |  | Apr- Jun | X |  |
| 19 | NAMS upgrade |  | Jan-23 | X | Installed NAMS |
| 20 | Testing |  | Feb-23 | X | Tested NAMS |
| 21 | Deployment |  | Mar-23 | X | NAMS Functional |
| 22 | Capacity Building |  | Apr- Jun 23 | X | Trained Staff |
|  | Emerging Issues: National & International Focus |  |  |  |  |
| 23 | Nigeria EITI validation 2023 Project |  | Aug-23 | X | Satisfactory Validation Status |
| 24 | Contract Transparency Implementation CT Project (Framework) |  | Jan-Dec | X | Developed CT Framework |
| 25 | Energy Transition |  | Oct-23 | X | Road Map Implementatio n Report, Future Minerals, Natural Gas financing |
| 26 | Update of E.I Beneficial Ownership Register Project |  | Jan-Dec | X | Updated BO Register |
| 27 | Support the development of the Framework for Illicit Financial Flows (IFFs) risk assessment in the EI |  | Aug | X | Developed IFF framework |
| 28 | Framework for analyzing Licensing rounds in the EI sector. |  | Jun-23 | X | Action Plan on Reconciliation Recommendati ons |
| 29 | Framework on Gender & Environment reporting in EITI |  | May-23 | X | Developed Gender & Environment Framework |
| 30 | Deepen B. O transparency through Open Ownership and EITI program on Opening Extractives |  | Jan-Dec | X | Improved EI Data |

| 31 | Produce an SOP/ Manual for all audit processes. |  | Sep-23 |  | X |  | EITI Transparency Report |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 32 | Comprehensive Review of NEITI Audit Data Template to reflect contemporary Issues & Non- negotiable quality and integrity of NEITI reports |  | Jan- Dec |  | X |  | Improved Data |
| 33 | Implementation of the NEITI Mainstreaming strategy |  | Apr-23 |  | X |  | Data Mainstreamed |
| 34 | Populate and publish EITI Transparency and Summary Data Template |  |  |  |  | X | Timely Transparency and Summary Data Template Report |
| 35 | Update of NEITI Data Dashboard |  |  |  |  | X | Update of NEITI Data Dashboard |
| 36 | Beneficiation in the solid minerals (Conduct an assessment) |  |  | X |  |  | Assessment report |
| 37 | The Impact of 13% derivation on relevant states |  |  |  | X |  | Impact Report |
| 38 | A study of financing options for beneficiation of the solid minerals sector of Nigeria (Impact assessment) |  |  | X |  |  | Impact Report |
| 39 | Opening Extractives Project |  |  |  | X |  | Deepening BO transparency in Nigeria |
| 40 | Review of NEITI 2021 Industry Reports |  | July – Sept 2023 |  |  | X |  |
| 41 | Engagements with the National Assembly on NEITI Industry Reports. |  | June, Sept, Oct, Nov, Dec |  | X |  |  |
| 42 | Minister of finance visit to NEITI House- launch of reports on gender and environment reports |  | 16th May 2023 |  |  | X |  |
| 43 | NEITI response to validation |  | April |  |  | X |  |
| 44 | BPSR Official Visit to NEITI |  | August 2023 |  |  | X |  |
| 45 | National Dialogue on Subsidy Removal organized by USAID |  |  |  |  | X |  |
| 46 | Nigeria International Pipeline and Security Conference |  | 6th Nov 2023 |  |  | X |  |
| 47 | NEITI Participation at the Nigeria Mining week |  | 16th - 18th Oct 2023 |  |  | X |  |
| 48 | Nigeria International Pipeline and Security Conference |  | 6th Nov 2023 |  |  | X |  |
| 49 | National Dialogue on Subsidy Removal organized by USAID |  |  |  |  | X |  |
| 50 | Supported on the development of Framework on Gender & Environmental reporting in EITI |  |  |  |  | X |  |
| 51 | Energy Transition Roadmap |  |  | X |  |  |  |
| 52 | Policy Engagement and Launch of Gender Reporting and Inclusion Framework |  | Jan – May |  |  | X |  |
| 53 | Supported the development of Nigeria’s corruption typology report |  | Jun – Nov 2023 |  |  | X |  |

|  | by Nigerian Financial Intelligence Unit. |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 54 | NRGI coaching on natural resources governance |  |  |  |  | May – July 2023 |  |  |  | X |  |
| 55 | Energy Transition Update of E.I Beneficial Ownership Register Project |  |  |  |  | Oct, Jan, Dec 2023 |  |  | X |  |  |
| 56 | Policy Engagement and Launch of Environmental Framework |  |  |  |  | Jan – May 2023 |  |  |  | X |  |
| 09 |  | 13 | 34 |  |  |  |  |  |  |  |  |

| S/N | ACTIVITY | OBJECTIVE | START/E ND MONTH | STATUS OF ACTIVITY (ITEMS REMOVED FROM WP SHOULD BE MARKED AS NOT STARTED.) |  |  | OUTCOME |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | FROM WORK PLAN | STRATEG IC | FROM WORK PLAN | NOT STARTED | IN PROGRESS | COMPLETED | AS STATED IN THE WORK PLAN |
|  | Finance and Account Support | Achieve operational excellence in implementing NEITI mandate through Professionalism, innovation, use of technology, resource management, and capacity building. |  |  |  |  |  |
| 1 | Fixed Asset Management (Financial statement conversion) |  | Q1-Q4 |  | X |  | Improved F/A Register |
| 2 | Implementing Integrated personnel payroll Information System (IPPIS) -UPGRADE |  | Q1-Q4 |  | X |  | Timely Salary Payment |
| 3 | Implementing Government Information Financial Information System (GIFMIS) -Cash plan module |  | Q1-Q4 |  | X |  | Improved GIFMIS Platform |
| 4 | Implementing New Accounting enterprise resource software to GAAP, IPSAS, and donor reporting. |  | Q1-Q4 |  | X |  | ERP Deployed |
| 5 | Training and certification for finance and account staff |  | Q1-Q4 |  |  | X | Certified ERP staff |
| 6 | Support service fee/upgrade for the accounting software |  | Q1-Q4 |  | X |  | True and Reliable Financial reports |
| 7 | Attending to External Key Stakeholders: OAGF, MOF, MOB&N P, FIRS, FCT Inland Revenue Service (Logistics) |  | Q1-Q4 |  | X |  |  |
| 8 | Statutory Audit of NEITI Account |  | Q1-Q4 |  |  | X |  |
| 9 | NSWG Sitting Allowance |  | Jan- Dec |  | X |  | Paid NSWG sitting |
| 10 | Round table meetings on compliance with covered entities |  | Jan- Dec |  | X |  | Improved compliance |
| 11 | Round Table Engagements with Stakeholders and NASS on Review of NEITI Act |  | Jun | X |  |  | Improved Stakeholders Buy-In |
| 12 | Review of NEITI Act |  | Jan-Dec |  | X |  | Amended Act |
| 13 | Development Of Risk Profile |  | Jan-Dec |  |  | X | Risk Profile Report |
| 14 | Workshop on Internal Audit Process and procedures |  | Apr & Sept |  |  | X | Worshop Report |
| 15 | Procurements, Advertisement, EOI, Technical & Financial bids Evaluations |  | Quarterly |  |  | X | Proc. EOIs |
| 16 | Pre-Bid Meetings |  | Mar & Jun |  |  | X | Award letters |
| 17 | Corporate auditor meeting |  |  |  |  | X |  |
| 18 | Software licenses |  |  |  |  | X |  |
| 19 | Annual Maintenance Contract for the building |  |  |  |  | X |  |
| 20 | Annual Maintenance Contract for the generator |  |  |  |  | X |  |
| 21 | Annual Maintenance Contract for ICT facilities |  |  |  |  | X |  |

STRATEGIC OBJECTIVE 3

| 22 | Consultancy on the NEITI industry report for Oil and Gas |  |  | X |  |
| --- | --- | --- | --- | --- | --- |
| 23 | Consultancy on the NEITI industry report for the solid minerals |  |  | X |  |
| 24 | EOI on the FASD report |  |  | X |  |
| 25 | EOI on the Study on PMS Consumption |  |  | X |  |
| 26 | Motor vehicles |  |  | X |  |
| 27 | Furniture and fittings |  |  | X |  |
| 28 | Data center project (Phase 1) |  |  | X |  |
| 29 | ICT equipment (Printers, photocopiers, laptops) |  |  | X |  |
| 30 | Car maintenance |  |  | X |  |
| 31 | ICT Maintenance |  |  | X |  |
| 32 | Fire extinguiher |  |  | X |  |
| 33 | Toners request |  |  | X |  |
| 34 | Drugs |  |  | X |  |
| 35 | Monitoring & Evaluation Activities |  | Jan-Dec | X | Improved WP Implementation |
| 36 | Legal Retainership |  | Jan- Dec | X | Suitable Legal Defence |
| 37 | Law Books |  | Jan-Dec 22 | X | Available law Books |
| 38 | Welfare of Staff |  | Jan-Dec 2022 | X | Improved Staff welfare |
| 39 | Staff Retreat |  | Q1 2022 | X | Motivated Staff |
| 40 | Training & Development |  | Jan-Dec 2022 | X | Improved staff Performance |
| 41 | Performance Management (Review and implementation) |  | Jan-Dec 2022 | X | Improved PMS |
| 42 | NYSC transport allowance |  | Jan-Dec 2022 | X | Improved Workforce |
| 43 | Office Renovation (Remodeling and partitioning) |  | Jan-Dec 2022 | X | Improved and conducive working environment |
| 44 | Maintenance of office building |  | Jan-Dec 2022 | X | Improved and conducive working environment |
| 45 | ICT Data Centre |  | Jan-Dec 2022 | X | Improved and conducive working environment |
| 46 | Purchase of Pool Cars |  | Jan-Dec 2022 | X | Improved and conducive working environment |
| 47 | Purchase of ACs & Electrical Fittings |  | Jan-Dec 2022 | X | Improved and conducive working environment |
| 48 | Purchase of materials, office supplies/stationaries & furniture and fittings (Fireproof cabinets, filing cabinets) |  | Jan-Dec 2022 | X | Improved and conducive working environment |

| 49 | Payment of utility bills (Electricity, Telephone, Water, Sewage, Tenement rate) |  | Jan-Dec 2022 |  | X | Improved and conducive working environment |
| --- | --- | --- | --- | --- | --- | --- |
| 50 | Maintenance services & safety (AC, Electricity, Plumbing, Furniture, vehicle, generator, fire extinguishers etc.) |  | Jan, May, Sept, Dec 2022 |  | X | Improved and conducive working environment |
| 51 | Fueling of generator & Pool Cars |  | Jan-Dec 2022 |  | X | Improved General Administration Functions |
| 52 | Other Services (Cleaning/Fumigation & Security |  | Jan, May, Sept, Dec 2022 |  | X | Improved General Administration Functions |
| 53 | Refreshment & Meals |  | Jan-Dec 2022 |  | X | Improved General Administration Functions |
| 54 | Courier Services |  | Jan, May, Sept, Dec 2022 |  | X | Improved General Administration Functions |
| 55 | Insurance |  | Jan-Dec 2022 |  | X | Improved General Administration Functions |
| 56 | Local Travels |  | Jan, May, Sept, Dec 2022 |  | X | Improved General Administration Functions |
| 57 | International Travels |  | Jan-Dec 2022 |  | X | Improved General Administration Functions |
| 58 | Hardware purchase |  | Jan-Dec 2022 |  | X | Improved General Administration Functions |
| 59 | Software purchase |  | Jan-Dec 2022 |  | X | Improved General Administration Functions |
| 60 | Internet bandwidth renewal/upgrade |  | Jan-Dec 2022 |  | X | Improved General Administration Functions |
| 61 | Consultancy services |  | Jan-Dec 2022 |  | X | Improved General Administration Functions |
| 62 | Website management & content |  | Jan-Dec 2022 |  | X | Improved Website |
| 63 | Subscriptions, Consumables & Others |  | Jan-Dec 2022 |  | X | Improved Consumable Support |
| 64 | Courtesy Visit by National Oil Spill Detection and Response Agency |  | 13th Sept 2023 |  | X |  |

| 65 | Natural Resource Governance Institute. Policy Dialogue on Nigeria Gas Plan |  |  | Aug 2023 |  |  |  | X |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 66 | OGP Inauguration of National Steering Committee |  |  | May 2023 |  |  |  | X |  |
| 67 | Partnered with Policy Alert to implement Policy Dialogue on Utilization of Beneficial Ownership Information on Crude Oil Swap Deals in Nigeria |  |  | April 2023 |  |  |  | X |  |
| 68 | Meeting with Ambassadors of Belgium, Canada and Australia |  |  | 30th Oct 2023 |  |  |  | X |  |
| 69 | Joining the dots with politically exposed persons in Nigeria |  |  | 29th Aug 2023 |  |  |  | X |  |
| 70 | Energy Transition and Climate Change in Nigeria |  |  | 27th June 2023 |  |  |  | X |  |
| 71 | One -Day Symposium on Energy Transition |  |  | 25th Oct 2023 |  |  |  | X |  |
| 72 | Engagement with CSOs coalition responsible for Growth Initiative for Fiscal transparency (GIFT) with intervention from USAID |  |  | 26th Oct |  |  |  | X |  |
| 73 | Courtesy visit of National coordinator of EITI Liberia |  |  | 9th June 2023 |  |  |  | X |  |
| 74 | National Extractives Dialogue NED 2023 |  |  | 14th – 15th Sept 2023 |  |  |  | X |  |
| 75 | Multi-stakeholder’s roundtable on the approval of NEITI 2021 Industry Report |  |  | 16th Aug 2023 |  |  |  | X |  |
| 76 | Civil Society Consultative Forum |  |  | 15th August 2023 |  |  |  | X |  |
| 77 | EITI Global Conference in Dakar 2023 |  |  | 13th – 14th June 2023 |  |  |  | X |  |
| 78 | Produced NEITI’s policy document/position paper submitted to the presidential committee (Special Investigation Panel) on oil theft |  |  | January 2023 |  |  |  | X |  |
| 79 | Management and coordination of NSWG meetings - NSWG Allowances - NSWG EITI activities |  |  | Jan - Dec |  | X |  |  |  |
| 80 | Valuation of the NEITI permanent office building |  |  | Q1 – Q4 | X |  |  |  |  |
| 81 | Fixed Asset Management (update of register since the acquisition of NEITI house and Financial. statement conversion) |  |  | Q1 – Q4 |  | X |  |  |  |
| 82 | Implementation of the digitization and security of financial records |  |  | Q1 – Q4 | X |  |  |  |  |
| 05 |  | 23 |  |  |  |  | 55 |  |  |
| OVERALL TOTAL=43 |  | OVERALL TOTAL =49 |  |  |  |  | OVERALL TOTAL =132 |  |  |

# Table 5 - Work Plan Implementation Status Summary

| Strategic Objectives | Completed | In Progress | Not Started | Total |
| --- | --- | --- | --- | --- |
| Objective 1 | 43 | 13 | 29 | 85 |
| Objective 2 | 34 | 13 | 09 | 56 |
| Objective 3 | 55 | 23 | 05 | 83 |
| Overall Total | 132 | 49 | 43 | 224 |
| % Average | 58.9% | 21.9% | 19.2% | 100% |

  - 1: FINDINGS:

The assessment exercise of the 2023 NEITI work plan implementation indicates that 58.9% of the programs and activities in the plan were completed, 21.9% were in progress, and 19.2% were not started at the end of December 2023.

This is a performance decline when compared with work plan implementation performances in the past years. The performance in 2019, 2020, and 2021 shows that 70%; 73%, and 71% of programs and activities in the work plan were respectively completed. Although, there was a 4.2% improvement in completion in the implementation of the work plan from 54.8% in 2022 to 58.9% in 2023.

The decline in the 2023 workplan implementation performance can be attributed to unrealistic programs and activities in the work plan; problems of non-adherence to implementation of the work plan; the failure to conduct a mid-year review of the work plan as at when due; inability to secure management’s approval for some programs and activities in the workplan; repetition of activities among others.

The exercise also reveals that while implementation of the NEITI’s strategic objective 2, which deals with sustaining extractive sector reporting, regular industry audits, disclosure, etc. recorded 60.7% of its activities as completed, the implementation of strategic objective 1, which deals with strengthening extractive sector governance and reforms, policy research, strategic stakeholder engagement, communication etc. recorded 50.6% of implementation. The implication of this is that it may be difficult to deliver on the accountability mandate of NEITI if this trend continues.

# CHALLENGES

The monitoring and evaluation exercise identified issues of non-adherence to the implementation of program and activities outlined in the work plan, duplication and unrealistic programs and activities in the plan, failure to conduct a mid-year review of the work plan as at when due, challenges in securing management’s approval for some activities and programs, as some of the challenges in the implementation of 2023 work plan.

# RECOMMENDATIONS

The management should ensure strict adherence to the implementation of program and activities outlined in the work plan; a prompt mid-year review of the work plan needs to be taken more

seriously. Besides, leadership approvals release of funds for programs and activities should be consistent with programmes and activities as itemized in the work plan.

The process of work plan development and implementation needs to be more robust and stakeholder-inclusive. Equal and adequate attention should be paid to the implementation of programs and activities across all the NEITI’s three strategic objectives. Capacity building for monitoring and evaluation team/focal persons across all the departments in the organization is strongly recommended. Finally, management need to expedite actions in the development of Monitoring & Evaluation Framework for the NEITI 2022-2026 Strategic Plan.