2017 Work Plan Evaluation Report

Nigeria Extractive Industries Transparency Initiative

NO. 60 NELSON MANDELA STREET, OFF KWAME NKRUMAH ASOKORO ABUJA

2017 Edition

Prepared By:  Planning Policy & Strategy Department.

Table of Content

Introduction	2

Overall Objective	2

2017 Work Plan Objectives	2

National Core Priority Objectives	2

Methodology	3

Basis of Evaluation	3

Executive Summary	3

The Goals are:	4

Table 2: General Performance Trend Analysis	5

Critical Success factor	5

Limitations	5

Recommendations.	6

Table 3: Activity report evaluation status.	7

Work plan costing	14

# Introduction

The 2017 work plan is an approved document, itemizing detailed action plans developed to guide the successful implementation of the NEITI strategic objective during the year. The work plan was developed in accordance with the key requirement of EITI reflecting national priorities and inputs from Government, Companies and the Civil Society.

# Overall Objective

The evaluation report objective is to assess the level of compliance and implementation of the work plan within the reporting time. The purpose is to ensure optimum compliance with the requirement 1.5 of the EITI standard, and to sustain the international best practice process, policy formulation review and implementation within the reporting year.

# 2017 Work Plan Objectives

The 2017 NEITI Work Plan is developed to consolidate on the change mantra of the FGN and to ensure successful transition of the 2013-16 NEITI Strategic plan to 2017-21, while awaiting the completion and approval of the new strategic goal 2017-2021.

The Plan is intended to:

I. Deepen the ongoing transparency and accountability drive in the extractive sector. `

II. Ensure International best practice in EITI Implementation, governance and resource management.

III. Promote the needed debate and advocacy for reforms in the country’s extractive industry.

# National Core Priority Objectives

The National priority objectives of the Federal Government of Nigeria include:

Economic Diversification

Corporate governance and Anti-corruption

State and Regional Development

Infrastructure and Social Development

Environmental protection

# Methodology

Modified Logical Framework Analysis (MLFA) was adopted for the 2017 work plan Evaluation. The template was populated on the basis of the 2017 approved work plan.

The work plan activities were evaluated on the basis of the information supplied by departments in filling the MLFA template and absolute conformity with the NEITI Financial Guidelines.

Activities evaluated were not necessarily completed within the Scheduled time frame as in the work plan but were completed within the Reporting period.

# Basis of Evaluation

- Activities were measured on the basis status (ie not started, in progress or completed) within the reporting period.

- Simple average of activities were taken to determine the success or otherwise of activities on % basis. (ie) number of activities in a status divided by the Total number of year activities multiplied by hundred.

- Activities are considered ‘in progress’ where financial commitments are made and not where the deliverables are not completed during the reporting period.

# Executive Summary

The evaluation of the NEITI work plan covers the period January- December 2017. The overall performance of the evaluation report indicated 62.85% of the activities were completed, 20% in progress and 17.15% not started as at reporting period. The breakdown is as shown below:

The evaluation covers 70 numbers of activities from 5 Department and covered 3 strategic Goals Namely

# The Goals are:

GOAL 1- Achieve Operational Excellence in Regulation and Enforcement across the Extractive Industries: To develop an effective comprehensive framework for the delivery of effective Audit, continuous Monitoring and Evaluation, stronger regulation, enforcement and compliance management.

The objective and priority is to ensure:

- Regular Reporting Industry Audits

- Data Automation

- Audit Remediation

- Research & Policy Development

- Business process Engineering

- Legal compliance of NEITI mandates. (Enforcement & regulation).

- Effective Monitoring & Evaluation

GOAL 2 - Attain Optimum Stakeholder Development in Extractive Industries Transparency and Accountability:  To develop a Robust Multi-Stakeholder Communication and Mobilization Strategy/Framework for effective stakeholder relationship management, collaboration and cooperation.

The objective and priority is  to deepen:

- Public Education, information and enlightenment on NEITI issues

- Publicity and Dissemination of NEITI audit Reports

- Cooperation with other anti- corruption agencies

GOAL 3 - NEITI Capacity Building: To develop Organizational and Funding Capacity to achieve the NEITI Mandate, Vision and Strategy.

The Objective is to sustain the:

- Implementation a financial management system that will ensure adequate funding & management of financial resources.

- Provide corporate governance of NEITI

- Maintain conducive working environment through effective management of facilities.

# Table 2: General Performance Trend Analysis

| YEAR | COMPLETED | IN PROGRESS | NOT STARTED |
| --- | --- | --- | --- |
| 2015 | 71.3% | 14.8% | 13.9% |
| 2016 | 56.82% | 30.68% | 12.5% |
| 2017 | 62.85% | 20% | 17.15% |
| Average | 63.65% | 21.82% | 14.51% |

The above table indicates that there has been significant improvement from year 2016- 2017, the number of planned activities increased from 56.82% in 2016 to 63.65% in 2017 while Planned activities in progress as at reporting date also reduced from 30.68% in 2016 to 20% in 2017. Activities not started increase d by 4%.

Generally in the year 2015 a lot has been achieved this is due to the fact that it is an election year and the government has released substantial funding to MDA,s while the dwindling economic fortune in the country in 2016 has affected funding to key sectors of the economy thereby affecting implementation of planned activities. Unlike in 2017, the economy has picked up and a concerted effort was made to attract funding from donor agencies to support and augment the planned activities.

# Critical Success factor

The critical success factor in the overall implementation of the NEITI work plan in the years under review has been funding & frequent changes in government policy directives.

# Limitations

•	The 2017 work plan did not make provision for adjustment of unforeseen implementation challenges such as funding & changes in the economic and political environment.

•	 The outcomes and performance indicators in some cases are ambiguous and not available thereby making evaluation process cumbersome.

•	 SMART Criteria need to be improved and adhered to (Specific, Measurable, Achievable, Relevance and Time bound).

# Recommendations.

- NEITI work plan should make provision for adjustment by continuous monitoring and routine reviews to take care of implementation challenges.

- A robust M&E framework is required in 2018 to adequately address the challenges on monitoring and evaluation in NEITI.

- Whilst developing the work plan, outcomes, performance indicators and outputs should be as SMART as possible.

- Activities should be broken into task and subtasks where need be to enable proper monitoring and assessment of the activity.

- Management to set out session for work plan development, the Planning Monitoring &Evaluation unit is to develop template to fit into strategic goal of NEITI to meet the EITI requirement.

- Capacity building is required for focal persons at departmental level to aid effective   work plan development and Monitoring & Evaluation function.

# Table 3: Activity report evaluation status.

| S/n | Activity | Objective | Start/End Month | KPI | Status of Activity (Items remove from WP should be mark not started .) |  |  | Output | Outcomes |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | From work plan |  | From work plan | From work plan | Not Started | In Progress | Completed | As stated in the work plan | As stated in the work plan |
| 1.10 | Oil and gas Audit 2015 | Achieve Regular Reporting in Industry Audits Achieve Regular Reporting in Industry Audits | July - December 2017 | Approved Oil & Gas Report |  |  |  | O&G Report | Improved Compliance to the EITI Requirements on Regular Audit Reporting. Improved Compliance to the EITI Requirements on Regular Audit Reporting |
| 1.11 | Solid Minerals Audit 2015 |  | July - December 2017 | Approve SM Report |  |  |  | SM Report |  |
| 1.12 | FASD Audit 2012/15 |  | July - December 2017 | Approve FASD Report |  |  |  | FASD Report |  |
| 1.13 | Value for Money Audit Scoping Study |  | Apr/2017 | Report |  |  |  | Report |  |
| 1.14 | Audit Progress, Monitoring and Evaluation |  | May-17 | Report |  |  |  | Audit Report |  |
| 1.15 | Revenue Management Tracking |  | Dec-17 | Report |  |  |  | Revenue Profie Report |  |
| 1.16 | Simplification of Audit Report |  | Dec-17 | Simplified Report |  |  |  | Simplified Report |  |
| 1.17 | Data Automation Infrasturcture | Improved NEITI Data Gathering process | Dec, 2017 | Installed Hard Ware |  |  |  | Installed Hard Ware | Improved Audit Process |
| 1.18 | Software Development |  | Dec, 2017 | Installed Information Mgt. System |  |  |  | Installed Information Mgt. System |  |
| 1.19 | Design and Develop Data Automation System |  | Dec, 2017 | Installed Information Mgt. System |  |  |  | Installed Information Mgt. System |  |
| 1.20 | Testing |  | Dec, 2017 | Report |  |  |  | Report |  |
| 1.21 | Deployment |  | Dec, 2017 | Report |  |  |  | Report |  |
| 1.22 | Beneficial Ownership Disclosure (Road Map Development & Implementation) | Improved B.O disclosure, data mainstreaming and enhanced remediation of the audits |  | Report |  |  |  | B.O Disclosure |  |
| 1.23 | Open Data Policy (Mainstreaming & EITI Implementation) |  |  | Report |  |  |  | Mainstreaming |  |
| 1.24 | Capacity Building |  | Dec, 2017 |  |  |  |  |  | No. of Reforms Initiated as a result of the Remediation |
| 1.25 | Manages and Tracks Implementation of Remediation Action Plan Items For Previous Audit(s) |  | Dec, 2017 | Resolve Issues from the Report |  |  |  | Report |  |
| 1.26 | Track and Recommend Steps on Policy Issues from the Audits |  | Aug-17 | Resolve Issues from the Report |  |  |  | Report |  |
| 1.27 | Outcome Assessment of all Remediation Activities |  | Jul-17 | Resolve Issues from the Report |  |  |  | Report |  |
| 1.28 | The Effect of the Decline in the Price of Crude Oil on the Oil & Gas Sector in Nigeria. | Conduct research to provide policy direction in line with evolving global trend in EI. | Apr/2017 | Policy Document |  |  |  | Research Report / Paper | Improved Policy advocacy, Legislative, Reviews and Review of Law/Act Policy. |
| 1.29 | Economic and Environmental Impact of Small Scale Mining Activities in Some Selected States |  | May/2017 | Policy Document |  |  |  | Research Report / Paper |  |
| 1.30 | Conduct Research to Provide Policy Direction in Line with Evolving Global Trend in Oil & Gas Industry |  | Jul/2017 | Policy Document |  |  |  | Research Report / Paper |  |
| 1.31 | Review of Existing Reforms in the Oil & Gas Sector |  | Aug/2017 | Policy Document |  |  |  | Research Report / Paper |  |
| 1.32 | Review of Existing Reforms in the Solid Minerals Sector |  | Mar-17 | Policy Document |  |  |  | Research Report / Paper |  |
| 2.01 | Legal Retainership | Ensure Regulation and enforcement of NEITI mandate. | Jan-Dec | Signed Contract |  |  |  | Signed Contract | Improved No. of compliance issues resolved and Amended NEITI act. |
| 2.02 | Round table meetings on compliance with covered entities |  | Mar- Nov | Minutes Of Meetings |  |  |  | Minutes Of Meetings |  |
| 2.03 | Development of a comprehensive framework for the Implementation and enforcement compliance with NEITI related laws and EITI Standards. |  | Oct | Signed MOU |  |  |  | Signed MOU |  |
| 2.04 | Purchase of E- books |  | Jun | E- Books |  |  |  | E- Books |  |
| 2.05 | Review of NEITI Act |  | Jan-Dec | Reviewed Act |  |  |  | Reviewed Act |  |
| 2.06 | Development of 2018 Annual work plan. | Effective Implementation of internal control Mechanism through continuous monitoring, auditing and improved procurement process. | Jan | Developed WP |  |  |  | Developed WP | Approved work plan Document. |
| 2.07 | Work Plan Monitoring, Implementation & Evaluation |  | Jan-Dec | M&E Reports |  |  |  | M&E Reports | M&E Report. |
| 2.08 | Development of EITI Annual Activity Report |  | May- Jun | EITI Report |  |  |  | EITI Report | EITI Annual Progress Report |
| 2.09 | Assist in desk review for Dev of NEITI strategic Plan 2017-20 |  | Jan Mar | Strategic Plan. |  |  |  | Strategic Plan. | Approved Strategic Plan Document |
| 2.10 | Assist in Dev of 2018 Annual Budget |  | Aug Sept | Annual Budget |  |  |  | Annual Budget | Draft 2018 Annual Budget. |
| 2.11 | Assist in Dev of MTSS and MTEF 2017-19 |  | Apr | MTSS |  |  |  | MTSS | MTSS Approved Document. |
| 2.12 | Development Of Risk Profile |  | Jan-Dec | Risk Profile Report |  |  |  | Risk Profile Report | Improved compliance to Standard operating procedures and practices. Improved compliance to Standard operating procedures and practices |
| 2.13 | Workshop on Internal Audit Process and procedures |  | Apr & Sept | Report |  |  |  | Create Awareness |  |
| 2.14 | Dev of Procurement Manual. |  | Jan-Dec | Procurement Manual. |  |  |  | Procurement Manual. |  |
| 2.15 | Procurement Hand Bills |  | Quarterly | Procurement Handbills. |  |  |  | Procurement Handbills. |  |
| 2.16 | Pre Bid Meetings |  | Mar & Jun | Bid Meetings |  |  |  | Bid Meetings |  |
| 3.01 | Simplification of NEITI Industry Audit Reports-Oil & Gas and Solid Minerals with infographics | To Disseminate NEITI Industry audit to strategic stakeholders and the general public for use to hold Government accountable. | Oct.-Nov. 2017 | Simplified Audit reports |  |  |  | Copies of simplified audit reports | Increased citizens awareness and understanding of NEITI audit reports |
| 3.02 | Development and production of fact sheets on NEITI Audit reports and processes. |  | Nov. 2017 | Eight fact sheets on issues contained in NEITI Audit reports |  |  |  | Copies of fact sheet made available to the public | Increased citizens awareness and understanding of NEITI audit reports |
| 3.03 | Engagements on NEITI policy briefs. |  | March - Dec. 2017 | Four engagements on NEITI policy briefs on specific extractive industries issues held |  |  |  | Report of the events. | Increased citizens awareness and understanding of NEITI audit reports |
| 3.04 | Public presentation of the Industry Audit Reports |  | Nov. 2017 | Report of the presentation |  |  |  | Reports, attendance lists, news mentions/clips of the presentation, video recodings and photographs of the event | Increased citizens knowledge on NEITI mandate, issues in the EI and the 2014 audit reports |
| 3.05 | Presentation of the Reports in the Geo-political zones | To provide timely information, education and enlightenment on NEITI and NEITI activities and promote government reform initiative in the extractive sector | January-August 2-17 | Report of the zonal presentations |  |  |  | Reports, attendance lists, photographs, video recordings and news reportage of the events | Increased citizens knowledge on NEITI mandate, issues in the EI and the 2014 audit reports |
| 3.06 | Media campaigns on NEITI issues using both traditional and social media |  | Jan-Dec. 2017 |  |  |  |  | Media packs, attendance list, reports, news mentions and photographs. | Increased citizens knowledge on NEITI mandate, issues in the EI and the 2014 audit reports |
| 3.07 | Stakeholder's dialogue on the NEITI audit Reports |  | Dec. 2017 | Report of the dialogue with action points and next steps for the extractive industries |  |  |  | Communiques, reports, attendance lists, photographs, video recordings, news reportage of the events and actionable points. | Increased citizens knowledge on NEITI mandate, issues in the EI and the 2014 audit reports |
| 3.08 | Productions of short video clips on EI and NEITI issues for upload on NEITI |  | January-Nov. 2-17 | 12 video clips on NEITI related issues produced |  |  |  | Copies of the video clips |  |
| 3.09 | Production and broadcast of radio programme on EI and NEITI Activities; |  | Jan- Dec | No. of Radio broadcast, jingles & Reports |  |  |  |  |  |
| 3.10 | Civil Society and professional associations roundtable/capacity building Two capacity building programmes in the south and north of the country |  | May-Jun | No. of Zonal capacity building for CSO |  |  |  |  |  |
| 3.11 | Media Roundtable/capacity building | To broaden and deepen engagements with stakeholders at national and sub national level. | Apr-Nov | No. of Capacity Building for Media |  |  |  |  |  |
| 3.12 | Engagement with legislature |  | May -Jun | Reports of Legislative engagement. |  |  |  |  |  |
| 3.13 | Dialogue with State Executive Councils |  | Apr- Nov | Minutes of Meetings |  |  |  |  |  |
| 3.14 | Sensitisation workshop for state Assemblies |  | Apr- Nov | Reports of meetings |  |  |  |  |  |
| 3.15 | Town hall meetings in geo political zones FBOs etc. |  | Jan- Dec | Reports of Meetings |  |  |  |  |  |
| 3.16 | Campus Outreach |  | Feb - Oct | No. of Outreach flagged off. |  |  |  |  |  |
| 3.17 | Review of NEITI Communication Strategy |  | Mar- Aug | Reviewed Strategy Doc. |  |  |  |  |  |
| 4.01 | Scoping and Gap Analysis of ethics environment in Nigeria | Monitor and evaluate governance of anti-corruption initiatives. | Q1-Q4 | Report |  |  |  |  |  |
| 4.02 | Implementation of Budget Efficiency project |  | Q1-Q4 | KPI Developed |  |  |  |  |  |
| 4.03 | Gap Analysis Study on existing legal & policy Framework on B.O disclosure |  | Q1-Q4 | Report |  |  |  |  |  |
| 4.04 | Development of a platform for updating anti-corruption database | Conduct impact analysis and construct country specific indicators and tools for governance of anti-corruption monitoring | Q1-Q4 | Data Base Developed |  |  |  |  |  |
| 4.05 | Research Studies of Anti-Corruption and Governance Survey |  | Q1-Q4 | Report |  |  |  |  |  |
| 4.06 | Publication and Launch of Phase IV Scoping Survey Report |  | Q1-Q4 | Report |  |  |  |  |  |
| 4.07 | Adoption and Implementation of the National Anti-Corruption Strategy |  | Q1-Q4 | Adapted NACs |  |  |  |  |  |
| 4.08 | Development and publication of the TUGAR Policy (White Paper) Series |  | Q1-Q4 | No. of Policy Papers |  |  |  |  |  |
| 4.09 | Corruption Risk Assessment in MDAs |  | Q1-Q4 | Report |  |  |  |  |  |
| 4.10 | Implementation of the Integrity Plan in the MDG Related MDA |  | Q1-Q4 | No. of reforms Implemented. |  |  |  |  |  |
| 4.11 | Review of Nigeria's Implementation of the UNCAC (2nd Cycle) and implementation of the Remediation Plan for the 1st review Cycle |  | Q1-Q4 | Reviewed Docs |  |  |  |  |  |
| 4.12 | Joint Commemoration of the International Anti-Corruption Day. |  | Q4 | Ac Day Report |  |  |  |  |  |
| 5.01 | Financial Management control & compliance. | Achieve effective financial and adminstative support |  |  |  |  |  |  |  |
| 5.02 | Administration and support services |  |  |  |  |  |  |  |  |
|  | Total |  |  |  | 12 | 14 | 44 |  |  |

# Work plan costing

Summary of core priorities and funding of the work plan include:

| Core Priority | Total |  | FGN |  | Donor |  | Gap |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Regular Audit Reporting |  | 350,208,500.00 |  | 292,268,500.00 |  | 57,940,000.00 |  |
| Dissemination, Education & Public Enlightenment |  | 171,904,000.00 |  | 161,800,000.00 |  | 10,104,000.00 |  |
| Effective implementation of internal control mechanism |  | 16,850,000.00 |  | 16,850,000.00 |  | - |  |
| Monitor and evaluate governance and anti-corruption initiatives |  | 146,000,000.00 |  | 20,000,000 |  | 126,000,000.00 |  |
| To provide Human Resource Management & Secretariat support |  | 190,436,992.00 |  | 168,804,117.00 |  | 21,632,875.00 |  |
| Financial Support Services |  | 16,376,000.00 |  | 16,376,000.00 |  | - |  |
| Grand Total |  | 891,775,492.00 |  | 661,248,617.00 |  | 230,526,875.00 |  |