NIGERIA EXTRACTIVE INDUSTRIES TRANSPARENCY INITIATIVE (NEITI)

2022 WORKPLAN MONITORING AND EVALUATION REPORT

BY: POLICY, PLANNING AND STRATEGY DEPARTMENT

# LIST OF ACRONYMS & ABBREVIATIONS

APR	Annual Progressive Report

CT	Contract Transparency

E.I	Extractive Industries

EITI	Extractive Industries Transparency Initiative

FAAC	Federation Account Allocation Committee

FASD	Fiscal Allocation and Statutory Disbursement Audit FIRS	Federal Inland Revenue Service

GIZ	Deutsche Gesellschaft Fur Internationale Zusammenarbeit IMTT	Inter Ministerial Task Team

IPPIS	Implementing Integrated Personnel Payroll Information System IPSAS	International Public Sector Accounting Standards

M&E	Monitoring & Evaluation

MLFA	Modified Logical Framework Analysis

MSG	Multi-stakeholders Group

NAMS	NEITI Data Automation System

NEITI	Nigeria Extractive Industries Transparency Initiative NSWG	National Stakeholders Working Group

O&G	Oil & Gas

OAGF	Office of the Accountant General of the Federation. PB	Policy Briefs

PIA	Petroleum Industry Act

SM	Solid Minerals

TUGAR	Technical Unit on Government and Anti-Corruption Reforms UNCAC		United Nations Convention Against Corruption

TABLE OF CONTENT

  - Introduction

  - NEITI 2022-2026 strategic plan objectives.

  - National Priorities

  - International Priorities

  - EITI Strategic Priorities

  - 2022 Workplan Objectives

  - 2022 Workplan Monitoring & Evaluation Objectives

  - Methodology

  - 2022 Workplan Performance Analysis

  - Four years Workplan Performance Trend Analysis

  - Workplan Implementation Status Table

  - Findings

  - Challenges

  - Recommendations

# EXECUTIVE SUMMARY

The monitoring and evaluation report for the 2022 EITI country work plan is the first in the implementation of the NEITI 2022-2026 Strategic Plan. The monitoring and evaluation exercise tracks and documents performance and progress recorded in implementing the NEITI 2022 work plan.

The work plan is designed and implemented to achieve the strategic plan objectives, deepen implementation of the Extractive Industries Transparency Initiative (EITI) in Nigeria, sustain the ongoing reforms in the oil, gas, and mining sectors, and address the country’s national priorities. The monitoring and evaluation exercise was carried out in compliance with Requirement 1.5 of the EITI 2019 Standard. The exercise is conducted using the NEITI’s monitoring and evaluation framework.

From the assessment exercise, the 2022 NEITI work plan implementation indicates that 54.76% of the programs and activities in the plan were completed, 21.43% were in progress, and 23.81% were not started at the end of December 2022. This is a decline in performance when compared with work plan implementation performances in the past three years. The performance in 2019, 2020, and 2021 shows that 71%; 73%, and 70% of programs and activities in the work plan were respectively completed.

The decline in the 2022 workplan implementation performance can be attributed to unrealistic programs and activities in the work plan; problems of non-adherence to implementation of the work plan; the failure to conduct a mid-year review of the work plan; inability to secure management’s approval for some programs and activities in the workplan; and repetition of activities among other factors.

The exercise also reveals that while implementation of the NEITI’s strategic objective 2, which deals with sustaining extractive sector reporting, regular industry audits, disclosure, etc. recorded above 70% of its activities as completed, the implementation of strategic objective 1, which deals with strengthening extractive sector governance and reforms, policy research, strategic stakeholder engagement, communication etc. recorded less than 30% of its activities completed. The implication of this is that it may be difficult to deliver on the accountability mandate of NEITI if this trend continues.

The report recommend that management should ensure strict adherence to the program and activities outlined in the work plan; a prompt mid-year review of the work plan needs to be taken more seriously. Besides, leadership approvals release of funds for programs and activities should be consistent with items in the work plan.

The process of work plan development and implementation needs to be more robust and stakeholder-inclusive. Equal and adequate attention should be paid to the implementation of programs and activities across all the NEITI’s three strategic objectives. Capacity building for monitoring and evaluation of staff/focal persons across all the departments in the organization is recommended.

# INTRODUCTION

The 2022 work plan is the first in the implementation of the NEITI 2022-2026 strategic plan. The activities and programs in the work plan were designed and implemented to achieve the strategic plan objectives, namely: to strengthen extractive sector governance and reforms through policy research, strategic stakeholder engagement, communication, and inter-agency collaboration; to sustain extractive sector reporting  and relevance by focusing on national and international priorities; and to achieve operational excellence in implementing the NEITI mandate through professionalism, innovation, use of technology, resource management, and capacity building.

The 2022 work plan outlined detailed action plans and mapped performance indicators developed to guide the implementation of the NEITI strategic objectives within the reporting period. The work plan was developed by the key requirement of EITI while its contents were tailored to reflect national priorities. The plan was also designed to strengthen the EITI implementation in Nigeria by addressing emerging  global issues in the EITI process and improving revenue for the government.

The program and activities outlined in the 2022 work plan were broader in scope, strategic in value addition to the EITI process, and tailored to meet national and international commitments and timelines on EITI validation. The monitoring and evaluation exercise was done in compliance with Requirement 1.5 of the 2019 EITI  Standard. The exercise is conducted using the NEITI’s monitoring and evaluation framework.

# NEITI 2022-2026 STRATEGIC OBJECTIVES:

Strategic Objective 1: Strengthen extractive sector governance and reforms through policy research, strategic stakeholder engagement, communication, and inter-agency collaboration.

Strategic Objective 2: Sustain extractive sector reporting and relevance by focusing on national and international priorities

Strategic Objective 3: Achieve operational excellence in implementing the NEITI mandate through professionalism, innovation, use of technology, resource management, and capacity building.

# NEITI Vision

A Nigeria whose extractive sector is transparent, accountable, and beneficial to all.

# NEITI Mission

To institutionalize accountability mechanisms and processes to instil a culture of transparency

and participation in Nigeria’s extractive sector for the benefit of all.

# NEITI 2022 WORK PLAN OBJECTIVES

The 2022 NEITI work plan was designed to consolidate and deepen EITI implementation in Nigeria by ensuring transparency and accountability in the application, reporting, and management of extractive revenues for the public good. The specific objectives are to

- Improve reporting on current and emerging issues through comprehensive data source mapping.

- Sustain extractive sector governance through regular timely, Qualitative industry reports with insightful recommendations for growth.

- Improve reporting through automation of the data-gathering process.

- Enhance the relevance of NEITI’s work by focusing on national and international priorities

- Broaden and deepen stakeholder base, national and sub-national engagement, and reporting in the extractive sector.

- Conduct research and studies to strengthen and influence policy reforms in the extractive sector.

- Influence timely implementation of audit recommendations and reports.

- Increase Public understanding and access to NEITI reports, knowledge products, and the EITI principles and process through regular dissemination and outreach.

- Facilitate public sector accountability through monitoring and evaluation of governance initiatives, internal control, and database coordination.

- Optimize efficiency and effectiveness in financial and human resources application and management

# NATIONAL PRIORITIES:

The national priorities of the Federal Government of Nigeria itemized below as contained in the Medium-Term National Development Plan 2022- 2025 were incorporated in the plan.

- Build a thriving and sustainable economy

- Attain energy sufficiency in power and petroleum products.

- Build a system to fight corruption, improve governance, and create national cohesion.

# INTERNATIONAL PRIORITIES:

The International priorities itemized below as contained in the 2019 EITI standard were considered and incorporated into the plan.

- Commodity Trading Transparency

- Environmental Disclosures

- Opening Extractives

- Gender Reporting

- Energy Transition

- Beneficial Ownership Disclosure

# WORK PLAN MONITORING & EVALUATION OBJECTIVE

The objective of the monitoring and evaluation exercise is to track and document performance and progress recorded in the implementation of the work plan, to help achieve the strategic plan objectives, deepen implementation of the Extractive Industries Transparency Initiative (EITI) in Nigeria, sustain the ongoing reforms in the oil, gas, and mining sectors and address the country’s national priorities and ensure compliance with requirement 1.5 of the EITI 2019 standard.

# METHODOLOGY:

The monitoring and evaluation exercise for the NEITI 2022 work plan adopted a Modified Logical Framework Analysis (MLFA). The exercise involved designing of monitoring and evaluation data collection template which was populated by various NEITI departments/units implementing different aspects of the work plan based on the status of activities and programs in the work plan as of December 2022. The data and information in the populated template were therefore collated, analysed, and evaluated by NEITI’s Planning, Monitoring, and Evaluation unit, and form the basis for the content of this report. The program and activities in the work plan were analysed and evaluated using the following approach:

- Program/activities were measured based on status (i.e. not started, in progress, or completed) as of December 2022.

- Programs/activities are considered “Completed” when they deliver expected outcomes by December 2022.

- Programs/activities are considered ‘In Progress’ where there is clear evidence(s) that such programs and activities have commenced within the reporting period.

- Programmes/activities are considered not ‘started ‘where it has not commenced as of the end of December 2022.

- A simple average of programs/activities was taken to arrive at a percentage analysis of the work plan implementation performance. This is done by dividing the number of programs/activities in status by the total number of the year’s activities multiplied by a hundred.

# PERFORMANCE EVALUATION BY STRATEGIC OBJECTIVES

Strategic Objective 1: An evaluation of activities under this objective indicates that 28.9% of the planned activities were completed, 37.8% are in progress and 33.3% could not start at the end of the reporting year.

Strategic Objective 2: An evaluation of activities under this objective shows that 73.529% of the planned activities were completed, 14.706% were in progress and 11.765% have not started as of the end of December 2022.

Strategic Objective 3: An evaluation of activities under this objective indicates that 66% of the planned activities were completed, 25.5% were in progress, and 8.5% were not started as of the end of the year.

# Work Plan Performance by Strategic Objectives Table

The analysis of work plan implementation by strategic objectives is represented in the table and chart below.

# Table 1: Performance by Strategic Objectives table (%)

| Strategic Objectives | 1 | 2 | 3 |
| --- | --- | --- | --- |
|  | Strengthen extractive sector governance and reforms through policy research, strategic stakeholder engagement, communication, and inter- agency collaboration | Sustain extractive sector reporting and relevance by focusing on national and international priorities | Achieve operational excellence in implementing the NEITI mandate through professionalism, innovation, use of technology, resource management, and capacity building |
| Completed | 28.9% | 73.5% | 66% |
| In Progress | 14.7% | 37.8% | 25.5% |
| Not Started | 11.8% | 33.3% | 8.5% |

OBJECTIVES PERFORMANCE CHART

Completed	In Progress	Not Started

O B J E C T I V E  1

O B J E C T I V E  2

O B J E C T I V E  3

.529%

%

Figure 1: Performance by Strategic Objective

  - OVERALL WORK PLAN IMPLEMENTATION/PERFORMANCE:

The assessment of the overall performance in the implementation of the 2022 NEITI work plan indicates that 54.76% of the programs and activities in the 2022 work plan were completed, 21.43% were in progress, while 23.81% were not started at the end of December 2022. The assessment is represented in the table, chart, and graph below:

# Table 2: Summary of Overall Work Plan Implementation/Performance:

| Strategic Objectives | Completed | In Progress | Not Started | Total |
| --- | --- | --- | --- | --- |
| Objective 1 | 13 | 17 | 15 | 45 |
| Objective 2 | 25 | 5 | 4 | 34 |
| Objective 3 | 31 | 12 | 4 | 47 |
| Overall Total | 69 | 24 | 23 | 126 |
| % Average | 54.762% | 26.984% | 18.254% | 100% |

Figure 2: Performance assessment graph:

ACTIVITIES PERFORMANCE CHART

23

34

69

Completed	In Progress	Not Started

  - FOUR YEARS TREND ANALYSIS OF WORK PLANS PERFORMANCES:

The four-year trend analysis shows that the NEITI 2022 work plan implementation recorded a performance decline when compared with work plan performances in previous years. The work plan performance assessment in 2022 shows that 54.76% of programs and activities in the plan were completed, while 71%; 73%, and 70% of programs and activities in the work plan for years 2019, 2020, and 2021 respectively were completed. The performance decline in 2022 can be attributed to unrealistic planned programs and activities; non-adherence to implementation of the programs and activities in the work plan; the failure to conduct a mid-year review of the work plan;

inability to secure management’s approval for some programmes and activities; and repetition of activities among other factors.

# Table 3: Performance Trend Analysis (4 years)

| Year | Completed % | In Progress % | Not Started % |
| --- | --- | --- | --- |
| 2019 | 70 | 18 | 12 |
| 2020 | 73 | 23 | 4 |
| 2021 | 71 | 23 | 6 |
| 2022 | 55 | 21 | 24 |

Figure 4: Four Years Performance Trend Analysis

FOUR YEARS PERFORMANCE TREND ANALYSIS

80

70

60

50

40

30

20

10

0

2019

2020

2021

2022

Completed %	In Progress %	Not Started %

Strategic Objective 1

  - NEITI 2022 WORK PLAN IMPLEMENTATION STATUS TABLE Table 4

Strategic Objective 1

| S/n | Activity | Objective | Start/ End Mont h | Status of Activity (Items removed from WP should be marked as not started.) | Outcome |
| --- | --- | --- | --- | --- | --- |

|  | From work plan | Strategic | From work plan |  | Not Starte d | In Progre ss | Completed | As stated in the work plan |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Remediation of NEITI Audit Reports | Strengthen extractive sector governance and reforms through policy research, strategic stakeholder engagement, communication, and inter-communication, and interagency collaboration. |  |  |  |  |  |  |
| 1 | Development of 2020-21 Remediation Plan |  |  | May 22 |  |  |  | Remediation Plan Doc |
| 2 | Conduct a review and assessment of the status of the NEITI audit recommendations. |  |  | Mar 22 |  |  |  | Reviewed Report |
| 3 | Re-activate and strengthen Inter- Ministerial Task Team (IMTT) |  |  | Mar 22 |  |  |  | No. of IMTT Resolutions |
| 4 | Collaboration with government agencies at the highest levels on issues identified by policy briefs/papers, Audit |  |  | Jan – Dec 22 |  |  |  | No of Decision Executed |
|  | Strategic Policy Research & Studies |  |  |  |  |  |  |  |
| 5 | Conduct research on fiscal regimes in the mining sector |  |  | Jan – Oct 22 |  |  |  | Improved FR in the Mining Sector |
| 6 | Conduct a study on the implications of the Petroleum Industry Act (PIA) on Extractive Industry Transparency and Accountability |  |  | Jan – Jul 22 |  |  |  | Improved PI sector reform & and accountability |
| 7 | Conduct a study on Gender and Environmental implications of EI activities |  |  | Q2 – Q3 |  |  |  | Framework for Gender & Env. |
| 8 | Conduct exploratory studies on issues in the extractive sector value chain |  |  | Q2 – Q3 |  |  |  | No of Influenced Policy Reforms |
| 9 | Produce policy briefs & papers on EI issues. (Research & Studies) |  | Jan- Dec |  |  |  |  | PP&PB |
| 10 | Conduct policy dialogue on findings of research on fiscal regime in the mining sector |  | Q1 – Q4 |  |  |  |  | No. of Policy Reforms |

| 11 | Research Studies of Anti- Corruption and Governance Survey |  | Q1 - Q4 |  |  |  | Monitoring Implementatio n of the PFM Systems |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 12 | Development and publication of TUGAR Policy Briefs and stakeholder engagement on the briefs |  | Q1 – Q4 |  |  |  | Published Policy Papers |
| 13 | FAAC Quarterly Reviews & Occasion papers |  | Q1 – Q4 |  |  |  | Knowledge Product |
| 14 | Development of 2022- 2024 MTSS & Implementation |  | Q1 – Q2 |  |  |  | MTSS Doc Developed |
|  | Stakeholders Engagement |  |  |  |  |  |  |
| 15 | Review and update stakeholders' map |  | Jun 22 |  |  |  | Improved Stakeholders |
| 16 | Develop a framework for stakeholders’ engagement |  | Jun 22 |  |  |  | Framework Developed |
| 17 | Identify and engage policy champions on NEITI issues |  | Mar 22 |  |  |  | Informed Champions |
| 18 | Conduct targeted engagements with government at the highest levels on issues identified by NEITI audit recommendations, policy briefs/papers |  | All year |  |  |  | No .of Policy Outcomes |
| 19 | Stakeholders Engagement on NEITI country work plan & 2021 Annual Progress Report (APR) |  | Mar 22 |  |  |  | Approved WP |
| 20 | Engage with relevant agencies on public registers of licenses, contracts, and data mainstreaming. |  | Apr 22 |  |  |  | Improved Mainstreamed Data |
| 21 | Engagement with relevant government agencies on Gender and Environment in E.I sector roles and implications |  | Apr 22 |  |  |  | Improved Gender Participation ES. Improved ES Environment |
| 22 | Stakeholders Engagement on NEITI Audit Reports. (Civil Society, Media, |  | Jan – Dec 22 |  |  |  | Informed Stakeholders |

|  | Legislators, FBOs, and Zonal Engagements) |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 23 | Design Framework for Social Media Engagement |  | Mar |  |  |  | Improved Social Media Engagement |
| 24 | Bilateral and Multilateral Engagement with Covered Entities to Achieve Systematic Disclosure |  | Apr |  |  |  | Improved Data Disclosure |
| 25 | Development of Framework for Sub- National Engagement |  | Apr |  |  |  | No. of Sub- National Engagements (Wider Outreach) |
|  | Communications, Dissemination & Advocacy |  |  |  |  |  |  |
| 26 | Publication & Printing of NEITI Industry Audit Reports (2020) |  | Jan- Jun 22 |  |  |  | Printed copies of reports |
| 27 | Lunching & Public Presentation of NEITI Industry Audit reports |  | Mar – Jun 22 |  |  |  | Published Reports |
| 28 | Dissemination of NEITI Reports to Stakeholders & Geo political Zones |  | Jan – Oct |  |  |  | Informed accountability actors |
| 29 | Simplification of NEITI Industry Audit Reports 2020 |  | Mar – Jun |  |  |  | Simplified reports |
| 30 | Quarterly press briefings/conferences on NEITI’s activities & operations |  | Mar – Dec 22 |  |  |  | Improved citizens Outreach |
| 31 | Publish Annual Work Plan 2022 and Progress Report (APR 2021) |  | Jan – Jun |  |  |  | Improved EITI Implementatio n Outcomes |
| 32 | Production of IEC materials |  | Jan- Mar |  |  |  | Branded IEC materials |
| 33 | Consumable for DM machine and Subscriptions to Communication software |  | Apr- Aug |  |  |  | Improved Communicatio ns Materials |
| 34 | Media campaign/radio program on natural resource governance at subnational levels |  | Jan – Dec |  |  |  | Improved citizens Outreach |

| 35 |  | Publish and disseminate NEITI’s report and knowledge products |  |  |  |  | Jan- Mar |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 36 |  | Design a framework for tracking public use of NEITI Data and information |  |  |  |  | Jun |  |  |  | NEITI Data Tracker |
|  |  | Inter-Agency Collaboration |  |  |  |  |  |  |  |  |  |
| 37 |  | Follow-up activities on TI-CPI analysis and the implementation of Executive Order 1 |  |  |  |  | Q1 – Q4 |  |  |  | Better implementatio n of Executive Order 1 |
| 38 |  | Follow-up activities on the TUGAR Ethics Survey and Gap Analysis |  |  |  |  | Q1 – Q4 |  |  |  | Implementatio n of Ethics Manual |
| 39 |  | Development of a platform for updating the anti-corruption database |  |  |  |  | Q1 – Q4 |  |  |  |  |
| 40 |  | Implementation of the National Anti-Corruption Strategy (Monitoring and Evaluation) |  |  |  |  | Q1 – Q4 |  |  |  | Better implementatio n of the NACS |
| 41 |  | Corruption Risk Assessment in the Nigerian Ports - Implementation of Integrity Plan |  |  |  |  | Q1 – Q4 |  |  |  |  |
| 42 |  | Updating of the Integrity Plan in the MDG Related MDAs |  |  |  |  | Q1 – Q4 |  |  |  |  |
| 43 |  | Review of Nigeria's Implementation of the UNCAC - Implementation of the Remediation Plan for the 1st & 2nd review cycles. |  |  |  |  | Q1 – Q4 |  |  |  |  |
| 44 |  | Coordination of the Anti- Corruption Agencies on the platform of the IATT |  |  |  |  | Q1 – Q4 |  |  |  | Increased cooperation |
| 45 |  | Joint Commemoration of the International Anti- Corruption Day |  |  |  |  | Q4 |  |  |  |  |
| 15 | 17 |  | 13 |  |  |  |  |  |  |  |  |

| S /n | Activity | Objective | Start/E nd Month | Status of Activity (Items removed from WP should be marked as not started.) |  |  | Outcome |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | From work plan | Strategic | From work plan | No t Sta rte d | In Prog ress | Co mpl eted | As stated in the work plan |
|  | Conduct a scoping study of all sector reports. | Sustain extractive sector reporting and relevance by focusing on national and international priorities. | Apr-22 |  |  |  |  |
| 1 | Scoping study for the Oil and Gas Sector. |  | Apr 22 |  |  |  | Improved Data, Evidence Source, and Quality of Audit report |
| 2 | Scoping study for the Solid Mineral Sector. |  | Apr-22 |  |  |  | Improved Data, Evidence Source, and Quality of Audit report |
| 3 | Scoping study for FASD |  | Apr 22 |  |  |  | Improved Data, Evidence Source, and Quality of Audit report |
| 4 | Oil and Gas Reconciliation Report 2021 |  | Sep 22 |  |  |  | Oil & Gas Industry Report |
| 5 | O &G Template Workshop |  | Jan 22 |  |  |  | Improved Data |
| 6 | Data collection exercise |  | Jan 22 |  |  |  | Data Collected |
| 7 | O&G Reconciliation and Validation exercise |  | Jan 22 |  |  |  | Reconciled & Validated Data |
| 8 | Solid Minerals Reconciliation Report 2021 |  | Feb 22 |  |  |  | SM Industry Report |
| 9 | SM Template Workshop for 3 locations |  |  |  |  |  | Improved Data |
| 10 | Data collection |  | Feb 22 |  |  |  | Reviewed templates |
| 11 | SM Reconciliation and validation meetings in 3 geopolitical zones |  | Aug-22 |  |  |  | Final SM report |
| 12 | SM stakeholders' engagement with Government Agencies |  | Mar 22 |  |  |  | Final SM report |
| 13 | FASD Reconciliation Report 2020 |  | Mar-may 2020 |  |  |  | FASD Report |
| 14 | FASD Template Workshop |  | Jul 22 |  |  |  | Improved Data |
| 15 | Data collection |  | Sep 22 |  |  |  | FASD Report |
| 16 | Reconciliation and Validation meeting |  | Mar 22 |  |  |  | Validated & Reconciled Data |
| 17 |  |  | Apr-Jun 22 |  |  |  |  |

| 18 | Data Automation System Infrastructure |  | Jan 22 |  |  |  | Installed NAMS |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 19 | Testing |  | Feb 22 |  |  |  | Tested NAMS |
| 20 | Deployment. |  | Mar 22 |  |  |  | NAMS Functional |
| 21 | Capacity Building |  | June 22 |  |  |  | Trained Staff |
|  | Emerging Issues: National & International Focus. |  |  |  |  |  |  |
| 22 | Nigeria EITI Validation 2022 Project |  | Aug 22 |  |  |  |  |
| 23 | Contract Transparency Implementation CT Project |  | Jan-Dec 22 |  |  |  | Developed CT Framework |
| 24 | Energy Transition (Framework) Road Map |  | Oct 22 |  |  |  | Developed Road Map |
| 25 | Update of E.I Beneficial Ownership Register Project |  | Jan –Dec 22 |  |  |  | Updated BO Register |
| 26 | Develop Framework for Illicit Financial Flows (IFFs) risk assessment in the EI |  | Aug 22 |  |  |  | Developed IFF framework |
| 27 | Framework for analysing Licensing rounds in the EI sector. |  | Jun 22 |  |  |  | Action Plan on Reconciliation Recommendations |
| 28 | Framework on Gender & Environment Reporting in EITI |  | May-21 |  |  |  | Developed Gender & Environment |
| 29 | Deepen B. O transparency through Open Ownership and EITI program on Opening Extractives. |  | Jan – Dec 22 |  |  |  | Improved EI Data |
| 30 | Produce an SOP/ Manual for all audit processes. |  | Sep 22 |  |  |  | EITI Transparency Report |
| 31 | Comprehensive Review of NEITI Audit Data Template to reflect contemporary Issues and non-negotiable |  | Jan –Dec 22 |  |  |  | Improved Data |
| 32 | Implementation of the NEITI Mainstreaming strategy. |  | Apr 22 |  |  |  | Data Mainstreamed |
| 33 | Populate and publish the EITI Transparency Template |  |  |  |  |  | Timely Transparency Report |
| 34 | Update of NEITI Data Dashboard |  |  |  |  |  | Update of NEITI Data Dashboard |

| Sub-total | 4 | 5 | 25 |  |
| --- | --- | --- | --- | --- |

# Strategic Objective 3

| S/n | Activity | Objective | Start/E nd Month | Status of Activity (Items removed from WP should be marked as not started.) |  |  | Outcome |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | From work plan | Strategic | From work plan | No t Sta rte d | In Pro gres s | Co mpl eted | As stated in the work plan |
|  | Finance and Account Support | Achieve operational excellence in implementing NEITI mandate through Professionalism, innovation, use of technology, resource management, and capacity building. |  |  |  |  |  |
| 1 | Fixed Asset Management (Financial statement conversion) |  | Q1-Q4 |  |  |  | Improved F/A Register |
| 2 | Implementing Integrated Personnel Payroll Information System (IPPIS) - RELEASE OF ADMINISTRATIO N TO MDAs |  | Q1-Q4 |  |  |  | Timely Salary Payment |
| 3 | Implementing Government Information Financial Information System (GIFMIS) -Cash plan module |  | Q1-Q4 |  |  |  | Improved GIFMIS Platform |
| 4 | Implementing New Accounting enterprise resource software to GAAP, IPSAS, and donor reporting. |  | Q1-Q4 |  |  |  | ERP Deployed |
| 5 | Training and certification for finance and account staff |  | Q1-Q4 |  |  |  | Certified ERP staff |
| 6 | Attending to External Key Stakeholders: OAGF, MOF, MOB&N P, FIRS, FCT Inland Revenue Service (Logistics) |  | Q1-Q4 |  |  |  |  |

| 7 | Statutory Audit of NEITI Account |  | Q1-Q2 |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  | HR, Administration, Logistics & IT Support |  |  |  |  |  |  |
| 8 | Welfare of Staff |  | Jan – Dec 2022 |  |  |  | Improved Staff welfare |
| 9 | Staff Retreat |  | Q1 2022 |  |  |  | Motivated Staff |
| 10 | Training & Development |  | Jan – Dec 2022 |  |  |  | Improved staff performance |
| 11 | Performance Management (Review and implementation) |  | Jan – Dec 2022 |  |  |  | Improved PMS |
| 12 | NYSC transport allowance |  | Jan – Dec 2022 |  |  |  | Improved Workforce |
| 13 | Office Renovation (Remodeling and partitioning) |  | Jan – Dec 2022 |  |  |  | Improved and conducive Working Environment |
| 14 | Maintenance of office building |  | Jan – Dec 2022 |  |  |  | Improved and conducive Working Environment |
| 15 | Resource Training Centre |  | Jan – Dec 2022 |  |  |  | Improved and conducive Working Environment |
| 16 | Purchase of Pool Cars |  | Jan – Dec 2022 |  |  |  | Improved and conducive Working Environment |
| 17 | Data Centre (data storage system) |  | Jan – Dec 2022 |  |  |  | Improved and conducive Working Environment |
| 18 | Purchase of ACs & Electrical Fittings |  | Jan – Dec 2022 |  |  |  | Improved and conducive Working Environment |
| 19 | Purchase of materials, office supplies/stationaries & furniture, and fittings (Fireproof cabinets, filing cabinets |  | Jan – Dec 2022 |  |  |  | Improved and conducive Working Environment |
| 20 | Payment of utility bills (Electricity, Telephone, Water, Sewage, Tenement rate) |  | Jan – Dec 2022 |  |  |  | Improved and conducive Working Environment |

| 21 | Maintenance services and safety (AC, Electricity, Plumbing, Furniture, vehicle, generator, fire extinguishers, etc.) |  | Jan, May, Sept, Dec 2022 |  |  |  | Improved and conducive Working Environment |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 22 | Fueling of generator & Pool Cars |  | Jan – Dec 2022 |  |  |  | Improved General Administration Functions |
| 23 | Other Services (Cleaning/Fumigatio n & Security |  | Jan, May, Sept, Dec 2022 |  |  |  | Improved General Administration Functions |
| 24 | Refreshment & Meals |  | Jan – Dec 2022 |  |  |  | Improved General Administration Functions |
| 25 | Courier Services |  | Jan, May, Sept, Dec 2022 |  |  |  | Improved General Administration Functions |
| 26 | Insurance |  | Jan-Dec 2022 |  |  |  | Improved General Administration Functions |
| 27 | Local Travels |  | Jan, May, Sept., Dec 2022 |  |  |  | Improved General Administration Functions |
| 28 | International Travels |  | Jan-Dec 2022 |  |  |  | Improved General Administration Functions |
| 29 | Hardware purchase |  | Jan-Dec 2022 |  |  |  | Improved General Administration Functions |
| 30 | Software purchase |  | Jan-Dec 2022 |  |  |  | Improved General Administration Functions |
| 31 | Internet bandwidth renewal/upgrade |  | Jan-Dec 2022 |  |  |  | Improved General Administration Functions |
| 32 | Consultancy services |  | Jan-Dec 2022 |  |  |  | Improved General Administration Functions |
| 33 | Website Management & content |  | Jan-Dec 2022 |  |  |  | Improved Website |
| 34 | Subscriptions, Consumables & Others |  | Jan-Dec 2022 |  |  |  | Improved Consumable Support |
|  | NSWG Governance & Internal Control |  |  |  |  |  |  |
| 35 | NSWG Sitting Allowance |  | Jan-Dec 2022 |  |  |  | Paid NSWG sitting |
| 36 | Round table meetings on compliance with covered entities |  | Jan-Dec 2022 |  |  |  | Improved compliance |

| 37 |  | Round Table Engagements with Stakeholders and NASS on Review of NEITI Act |  | Jun |  |  |  | Improved Stakeholders Buy-In |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 38 |  | Review of the NEITI Act |  | Jan-Dec 2022 |  |  |  | Amended Act |
| 39 |  | Development Of Risk Profile |  | Jan-Dec 2022 |  |  |  | Risk Profile Report |
| 40 |  | Workshop on Internal Audit Process |  | Apr & sept |  |  |  | Workshop Report |
| 41 |  | Procurements, Advertisement, EOI, Technical & Finance |  | Quarterly |  |  |  | Proc. EOIs |
| 42 |  | Pre-Bid Meetings |  | Mar & Jun |  |  |  | Award letters |
| 43 |  | Monitoring & Evaluation Activities |  | Jan-Dec 2022 |  |  |  | Improved WP Implementation |
| 44 |  | Legal Retainership |  | Jan-Dec 2022 |  |  |  | Suitable Legal Defense |
| 45 |  | Development of 2021 EITI Annual Progress Report |  | Jun 22 |  |  |  | Timely Report |
| 46 |  | Law Books |  | Jan-Dec 2022 |  |  |  | Available law Books |
| 47 |  | Development of the 2023 Country Work Plan |  | Sep 22 |  |  |  | Developed WP |
| 4 | 12 | 31 |  |  |  |  |  |  |
| 2 3 | 34 | 69 |  |  |  |  |  |  |

# Table 5 - Work Plan Implementation Status Summary

| Strategic Objectives | Completed | In Progress | Not Started | Total |
| --- | --- | --- | --- | --- |
| Objective 1 | 25 | 5 | 4 | 34 |
| Objective 2 | 13 | 17 | 15 | 45 |
| Objective 3 | 31 | 12 | 4 | 47 |
| Overall Total | 69 | 24 | 23 | 126 |
| % Average | 54.762% | 26.984% | 18.254% | 100% |

  - 1: FINDINGS:

The assessment exercise of the 2022 NEITI work plan implementation indicates that 54.76% of the programs and activities in the plan were completed, 21.43% were in progress, and 23.81% were not started at the end of December 2022.

The 2022 NEITI work plan implementation indicates that 54.76% of the programs and activities in the plan were completed, 21.43% were in progress, and 23.81% were not started at the end of December 2022. This is a performance decline when compared with work plan implementation performances in the past three years. The performance in 2019, 2020, and 2021 shows that 71%; 73%, and 70% of programs and activities in the work plan were respectively completed.

The decline in the 2022 workplan implementation performance can be attributed to unrealistic programs and activities in the work plan; problems of non-adherence to implementation of the work plan; the failure to conduct a mid-year review of the work plan; inability to secure management’s approval for some programs and activities in the workplan; and repetition of activities among other factors.

The exercise also reveals that while implementation of the NEITI’s strategic objective 2, which deals with sustaining extractive sector reporting, regular industry audits, disclosure, etc. recorded above 70% of its activities as completed, the implementation of strategic objective 1, which deals with strengthening extractive sector governance and reforms, policy research, strategic stakeholder engagement, communication etc. recorded less than 30% of its activities as completed. The implication of this is that it may be difficult to deliver on the accountability mandate of NEITI if this trend continues.

# CHALLENGES

The monitoring and evaluation exercise identified issues of non-adherence to the program and activities outlined in the work plan, duplication and unrealistic programs and activities in the plan, failure to conduct a mid-year review of the work plan, challenges in securing management’s approval for some activities and programs, as some of the challenges in the implementation of 2022 work plan.

# RECOMMENDATIONS

The management should ensure strict adherence to the program and activities outlined in the work plan; a prompt mid-year review of the work plan needs to be taken more seriously. Besides, leadership approvals release of funds for programs and activities should be consistent with items in the work plan.

The process of work plan development and implementation needs to be more robust and stakeholder-inclusive. Equal and adequate attention should be paid to the implementation of programs and activities across all the NEITI’s three strategic objectives. Capacity building for monitoring and evaluation of staff/focal persons across all the departments in the organization is recommended.