2021 Work Plan Evaluation Report. NIGERIA EXTRACTIVE INDUSTRIES TRANPARENCY INITIATIVE. NO.60 NELSON MANDELA STREET, OFF KWAME NKRUMAH ASOKORO ABUJA

Contents

Executive Summary:	2

Strategic Objectives Performance Review	2

Figure 1: General Performance chart	3

Introduction	4

Overall Objectives	4

2021 Work Plan Objectives	4

The NEITI 5 years Strategic objectives (2017-21) are:	5

Core National Objectives:	5

2021 Target Priority	5

Evaluation Methodology	6

Basis of Evaluation	6

General Performance Table	6

General Performance Trend Analysis (5 years)	8

Risk Factors	9

Mitigation Factors	10

Activities Status Evaluation Table	11

# Executive Summary:

The 2021 NEITI work plan is the last in the series of our 2017-21 Strategic plan. The work plan performance evaluation covers the period January- December 2021. The overall performance report indicates that 71% of the activities were completed, 23% in progress and 6% not started as at reporting period.

The 2021 evaluation shows a slight 2% decline in completed activities compared to the previous year, maintain status in progress activities and 2% increase in activities not started. The evaluation indicates a marginal 2% decline in general performance. This is because of the ambitious activities lined up as the last workplan in the series 2017-21 and transitional in developing new strategic plan 2022-26. All planned activities competing for limited resources funding in the face of the effect of the COVID 19 pandemic on the global economy.

## Strategic Objectives Performance Review

Objective 1: Activity review indicates that 70% of the planned activities were completed, 26.67% are in progress and only 3.33% could not start as at reporting timeline. This signify a marginal improvement of 2% against the 2020 objective one assessment.

Significant progress was made with the completion of the 2020 industry audits (Oil & Gas, Solid Minerals and the FASD) but were not approved by the MSG and made publicly available until in February 2022.

Milestone achievement was recorded with partnership of the NEITI/NNPC joint remediation committee which addressed and resolved 95% of the outstanding issues that frequent the Oil & Gas industry audit report recommendations.

The Passage of the PIA and subsequent signing into law by the president in August 2021 and follow up issues with NEITI being a member of the PIA presidential Implementation Steering Committee has broadened the scope of the EITI implementation in Nigeria. This has also shouldered additional responsibility for the organization and the lean available resources to prosecute our mandate and objectives.

Emerging issues in the EITI implementation such as Data Mainstreaming, Commodity Trading, Beneficial ownership disclosure, Energy transition, Gender and Environmental reporting are the new areas in our strategic direction that influence our 2021 performance.

Objective 2: Evaluation shows that 57.8. % of the planned activities were completed 35.5.% in progress while 6.7% have not started as at the reporting period. This is because of the research being conducted that are beyond the reporting period, and other studies that require inter-agency collaboration and support.

Lack of funding and the passage of the new law (PIA) affected some of the research activities planned which could not start as at reporting period.

Objective 3: Indicates that 65% of the planned activities was implemented within the reporting period 17.5 % is in Progress and 17.5. % not implemented (NOT STARTED).

Objective 3 recorded a marginal general improvement in performance of activities designed to implement strategic communication with critical stakeholders aimed at empowering accountability actors were conducted using a multi-dimensional approach. Adequate stakeholders buy-in are expected to broaden and deepen the process of extractive industry transparency and accountability in Nigeria during the reporting period.

Focus and deliberate effort were made to open communication with strategic stakeholders. The CSO, Media, NASS, Companies and the government through routine outreach activities and strategic engagement.

Objective 4: The Evaluation Indicates that activities designed to achieve Objective 4 were 91% completed and 9% in progress activities implementation, this slight reduction in performance level is due to lack of funding, change in management leadership in the secretariat and at the MSG level and the significant changing nature of the scope of EITI implementation at local and international levels.

Activities designed under this objective are mainly Human Administrative and Financial support to enhanced operational capacity, achieved excellence through effective administration and limited financial support from the Government and Donor Agencies.

The General performance of the 2021 work plan implementation is represented in the diagram below.

## Figure 1: General Performance chart

Figure 1 General Performance Chart

# Introduction

The 2021 workplan is the last in the series of our 2017-2021 strategic plan. The plan is developed to consolidate the achievement we have made from 2017 to date in realizing our strategic objectives of deepening openness in the extractive sector, shaping extractive sector overall governance reforms, strengthening demand for accountability, and developing operational capacity and legitimacy.

The 2021 plan is also designed to strengthen EITI Implementation in Nigeria by addressing emerging global issues in the EITI process.

While this plan is substantially compliance with requirement 1.5 of the EITI, it is also designed to align with national priority objectives of the FGN. The implementation of the 2021 work plan activities is broader in scope, strategic in in value addition to the EITI process and tailored to meet national and international commitments and timelines on EITI validation.

# Overall Objectives

The objective of the evaluation report is to assess the extent of the implementation of our 2021 work plan comparatively in achieving our 4 strategic long-term objectives while consolidating the gains recorded in successive years within the reporting period.

The monitoring and evaluation are conducted in line with the NEITI M&E framework, compliance with the requirement 1.5 of the EITI standard, and the international best practice & process of performance review within the reporting year.

## 2021 Work Plan Objectives

The 2021 NEITI Work Plan was tailored to consolidate the gains and deepen the process of EITI implementation in Nigeria by ensuring transparency and accountability in the application, reporting and management of extractive revenues in the EI sector for public good:

Achieve Regular & Timely Industry Audit & Reporting of the E.I Sector through:

- Automation of NEITI data gathering process.

- Implementation of remedial issues from the annual reconciliation report.

- Conduct research and empirical studies aimed at improving the management of mineral resources in line with evolving global standards in the extractive industry.

- Implementation of emerging EITI issues.

- Shape and Influenced policy decisions in the Industry through:

- Providing support for Policy development, reviews, and research.

- Review of policy reforms, advocacy, and engagements.

- Activities to monitor and evaluate governance initiatives in the extractive industry.

- Facilitate the building of synergy among diverse anti-corruption initiatives

- Strengthen demand for accountability by:

- Broadening and deepening the dissemination of NEITI Industry reports and research findings to multi-stakeholder groups.

- Strengthening the capacity of accountability actors to analyse and engage with extractive industry data.

- To provide Human Resource Management and effective administrative support to the Secretariat through:

- Provision of operational, and logistic support to the secretariat.

- Provision and management of adequate ICT support to the secretariat.

- Ensuring optimum compliance by the secretariat with reporting obligations.

- Maintain the highest standard in auditing and procurement process.

- To maintain high quality of accounting standards in the presentation of financial statements and reporting.

# The NEITI 5 years Strategic objectives (2017-21) are:

- Deepen openness in the extractive sector through timely audits and other impactful studies.

- Shape extractive sector and overall governance reforms through policy engagements, thought leadership and inter-agency coordination.

- To strengthen accountability in the use of extractive revenues through strategic communication with critical stakeholders and empowerment of accountability actors.

- To develop operational capacity, legitimacy and support through effective administration and human resource management and adequate funding.

## Core National Objectives:

The 2021 Work plan is focused on achieving the following National objectives as outline in the Federal Government’s 2021 budget proposal.

1.	Promote Economic Diversification

2.	Enhance Fiscal Transparency

3.	Enhance Competitiveness and Social Inclusion

4.	Improve Governance through reform initiatives

## 2021 Target Priority

The 2021 work plan is purposefully designed to support the national core priority objectives of governance by improving in governance and reform initiatives, amplified the fight against corruption and improve fiscal discipline in management of public spending.  The plan will also support Socio Economic Priority of the FGN to achieve Macroeconomic stability, improve efficiency & quality of capital spending on critical Infrastructures and maintain 7% GDP Growth, Broaden Revenue base, plug leakages and reduce fiscal deficit by 3% of GDP among other priority objectives.

# Evaluation Methodology

Modified Logical Framework Analysis (MLFA) was adopted for the 2021 work plan Evaluation. The template was populated based on the 2021approved work plan.

The work plan activities were monitored, implementation data collected and evaluated based on the information supplied by departments and stakeholders in filling the MLFA template and absolute conformity with the NEITI Financial Guidelines.

Activities evaluated were not necessarily completed within the scheduled time frame as in the work plan but were completed within the reporting period.

# Basis of Evaluation

- Activities were measured on the basis status (i.e. not started, in progress or completed) within the reporting period.

- Simple average of activities was taken to determine the success or otherwise of activities on % basis. (i.e.) number of activities in a status divided by the Total number of year activities multiplied by hundred.

- Activities are considered “Completed” when they are delivered within the reporting period.

- Activities are considered ‘In Progress’ where financial commitments are made, and deliverables are not completed during the reporting period.

- Activities are considered not ‘started ‘Where it has not commenced as at reporting period.

General Performance Table.

| Strategic Obj | 1 | 2 | 3 | 4 |
| --- | --- | --- | --- | --- |
| Completed | 70% | 57.8% | 65.% | 91% |
| In progress | 26.67% | 35.5% | 17.5% | 9% |
| Not started | 3.33% | 6.7% | 17.5% | - |

# General Performance Trend Analysis (5 years)

| YEAR | COMPLETED % | IN PROGRESS % | NOT STARTED % |
| --- | --- | --- | --- |
| 2017 | 62 | 20 | 18 |
| 2018 | 68 | 19 | 13 |
| 2019 | 70 | 18 | 12 |
| 2020 | 73 | 23 | 4 |
| 2021 | 71 | 23 | 6 |
| Avarage | 68.8% | 20.6% | 10.6% |

years General Performance Trend Analysis

(2017-2021)

Analysis:

The 5 years trend analysis shows steady strategic improvement in the activity’s completion from the year 2017-2020 i.e. 62%, - 73% in 2020 except for the year 2021 with marginal 2% decline which recorded 71% activities completion. The average activities implementation completion in the 5 years cycle of the strategic plan with four strategic objectives is 68.8%

significantly, the work plan activities evaluation indicate reduction in level of activities not started from 18% in 2017 - 4% in 2020. This could be attributed to the strategic, effective and efficient planning and implementation of the workplan. The 2021 scenario of 6% is as a result of factors identified earlier that are not within management or MSG control.

The year 2021 has been challenging due to leadership transition at management and MSG levels, and the effect of COVID 19 on the global economy and its adverse consequence.

New order has been explored with virtual technology to improve on the plans and activities. In general terms activities considered to be in progress has substantial financial commitment and in many cases their implementation will exceed one fiscal year.

# Risk Factors

NEITI critical success factors in the implementation of our 2021 set objectives are:

- Change in administrative and political leadership in management and MSG levels

- Funding: Funding has been the major success factor in achieving our mandate thus its timely and regular availability and accessibility will aid successful implementation of our programs and objectives.

- Management buys in the evolution process of domesticating monitoring and evaluation at all levels in the organization.

- Limited capacity of personal in the Monitoring and evaluation unit.

- Challenges of coping with the new world order on the COVID 19 protocol thus need to heavily invest in technology to support the virtual process.

# Mitigation Factors

- Donor Funding: NEITI will continue to approach our partners and willing donors to support our programs. Currently the World Bank, Ford Foundation, Rolac and the GIZ are supporting NEITI in the EITI implementation.

- Management to set out session for work plan development, the Planning Monitoring &Evaluation unit is to develop template to fit into strategic goal of NEITI to meet the EITI requirement.

- Capacity building is required for focal persons at departmental level to aid effective work plan development and Monitoring & Evaluation functions ion at the various levels.

2021 WP Implementation Evaluation Summary Table

| Strategic Objectives | Completed | In Progress | Not Started | Total |
| --- | --- | --- | --- | --- |
| Objective 1 | 21 | 8 | 1 | 30 |
| Objective 2 | 26 | 16 | 3 | 45 |
| Objective 3 | 15 | 4 | 4 | 23 |
| Objective 4 | 31 | 3 | - | 34 |
| Total | 41 | 13 | 2 | 132 |
| % of Performance | 71% | 23% | 6% |  |

# Activities Status Evaluation Table

| S/n | Activity | Objective | Start/End Month | KPI | Status of Activity (Items remove from WP should be mark not started.) |  |  | Outcome |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | From work plan | Strategic | From work plan | From work plan | Not Started | In Progress | Completed | As stated in the work plan |
| 1 | Oil and gas Audit 2020 | Deepen openness in the extractive sector through timely audits and other impactful studies. | Aug-21-Dec |  |  |  |  | Final report |
| 2 | O &G Template Workshop (unautomated templates) |  | Mar-21 |  |  |  |  | Reviewed templates |
| 3 | O&G Reconciliation and Validation exercise |  | Jul-21 |  |  |  |  | Reconciliation report |
| 4 | FASD Audit 2020 |  | Sep-21-Dec |  |  |  |  | FASD Report (final) |
| 5 | FASD Template Workshop |  | Mar-21 |  |  |  |  | Approved templates |
| 6 | Data collection |  | Apr- Jun 21 |  |  |  |  | Aggregated data |
| 7 | Reconciliation and Validation meeting |  | Aug-21 |  |  |  |  | Reconciliation report |
| 8 | Solid Minerals Audit 2020 |  | Sep-21 |  |  |  |  | SM report (final) |
| 9 | SM Template Workshop for 3 locations |  | Mar-21 |  |  |  |  | Draft templates |
| 10 | Data collection |  | Apr- Jun 21 |  |  |  |  | Aggregated data |
| 11 | SM Reconciliation and Validation meetings in 3 geopolitical zones |  | Aug-21 |  |  |  |  | Reconciliation report |
| 12 | Targeted engagement with Federal Mines Officers on the NEITI audit process |  | Jan- Dec 21 |  |  |  |  | Engagement report |
| 13 | Expansion of Data Automation Platform (NAMS) to capture outstanding data collection templates for the audit reconciliation |  | Mar-21 |  |  |  |  | Updated NAMs |
| 14 | Capacity Building for External Stakeholders |  | Jun-01 |  |  |  |  | Capacity building report |
| ,15 | Capacity Building for Internal Stakeholders |  | Aug-21 |  |  |  |  | Capacity building report |
| 16 | Engagement of IT support for the scaling up and capacity upgrade for the NAMS platform post deployment | Deepen openness in the extractive sector through timely audits and other impactful studies. | Sep-21 |  |  |  |  | Engagement of IT support personnel/ Functional NAMS |
| 17 | Provision for feedback collection, collation, and integration on the NAMS platform post deployment |  | Oct-21 |  |  |  |  | Feedback/Updated NAMs report |
| 18 | Development of framework to Integrate FAAC data to the annual audits |  | Sep-21 |  |  |  |  | Approved integration Framework |
| 19 | Dashboard data from automation output (create a linkage with NAMS platform) |  |  |  |  |  |  | Improved Data Dashboard link to NAMs System |
| 20 | Manage and track implementation of Remediation action plan Items from previous audit(s) and conduct outcome assessment of all remediation activities |  | All year |  |  |  |  | Tracking and outcome assessment reports |
| 21 | Track and Recommend Steps on Policy Issues from the annual Audits |  | All year |  |  |  |  | Policy proposals |
| 22 | Update the developed framework (by PPS) for remediation with active participation of TUGAR and anti-corruption agencies |  | Aug-21 |  |  |  |  | Updated framework |
| 23 | Strategic engagements on recommendations from all Audits |  | All year |  |  |  |  | Engagement reports |
| 24 | Review of Existing Reforms in the Oil & Gas Sector (PIB - in view, Amended DOA etc) |  | Feb-21 |  |  |  |  | Review report |
| 25 | Developing a framework for enforcing provisions of the NEITI Act on statutory agencies of government as it relates to the timely disclosure of information by the entities |  | Mar-21 |  |  |  |  | Approved Framework |
| 26 | Engagement with relevant government agencies on mainstreaming (DPR,FIRS, NDDC, NCDMB, NACCIMA, FMOF,FMPR,OAGF,CBN etc) |  | Apr-21 |  |  |  |  | Approved Engagement report |
| 27 | Engagement with relevant government agencies on contract transparency in the extractive sector | Deepen openness in the extractive sector through timely audits and other impactful studies. | Apr-21 |  |  |  |  | Approved Engagement report |
| 28 | Engagement with relevant government agencies on environmental matters in the extractive sector |  | May-21 |  |  |  |  | Approved Engagement report |
| 29 | Engagement with relevant government agencies on Gender issues in the extractives |  | May-21 |  |  |  |  | Approved Engagement report |
| 30 | Engagement with Corporate Affairs Commission on the provision for B.O data in the Amended CAMA, and the type and structure of the data to be captured and displayed by the B.O register domiciled at the CAC (in collaboration with MCO and DPR) |  | May-21 |  |  |  |  | Approved Engagement report |
| Sub Total Objective 1 |  |  |  |  | 1 | 8 | 21 |  |
| 31 | Review of 2017-21 Strategic Plan |  | Q2-Q3 |  |  |  |  | SP reviewed report |
| 32 | Development of 2022-2026 Strategic Plan |  | Q3-Q4 |  |  |  |  | 2022-26 SP developed |
| 33 | Development of MTSS 2022-2024 |  | Q4 |  |  |  |  | MTSS developed |
| 34 | Development of framework for Monitoring & Evaluation. |  | Q4 |  |  |  |  | M&E Framework Developed |
| 35 | Development of 2022 Annual work plan |  | Q3-Q4 |  |  |  |  | 2022 WP developed |
| 36 | EITI 2020 APR |  | Q1-Q2 |  |  |  |  | 2020 APR Developed |
| 37 | 2020 Activities Monitoring & Evaluation report |  | Q1-Q4 |  |  |  |  | M&E Report |
| 38 | Development of NEITI funding Strategy Document |  | Q3-Q4 |  |  |  |  | FS Developed |
| 39 | Compliance & disclosure strategy |  | Q3-Q4 |  |  |  |  | CDS Developed |
| 40 | HR/Adm Strategy |  | Q3-Q4 |  |  |  |  | HR/ADM strategy |
| 41 | Communication Strategy |  | Q3-Q4 |  |  |  |  | Comms Strategy |
| 42 | Research on Gender inclusion in the ownership and management of extractive industry assets |  | Q2-Q3 |  |  |  |  | Studies Report |
| 43 | Mapping of oil spill sites in the Niger Delta and response of stakeholders to them in the context of the mandate of NEITI. |  | Q2-Q3 |  |  |  |  | Mapping Report |
| 44 | FAAC Reviews |  | Q1-Q4 |  |  |  |  | FAAC Reviews |
| 45 | Review of reforms in the Extractive Industry 2015-2021 |  | Q1-Q4 |  |  |  |  | E.I reforms Report |
| 46 | Stakeholders’ engagement on impact of mining & 13% derivation. |  | Q1 |  |  |  |  | Stakeholders Engagements |
| 47 | Engagements on outcome of the NEITI/NNPC joint remediation Committee & other Remedial issues. |  | Q2-Q3 |  |  |  |  | Stakeholders Engagements |
| 48 | Stakeholders’ engagement on BO register and implication of amended CAMA |  | Q2-Q3 |  |  |  |  | Stakeholders Engagements |
| 49 | Development of Policy briefs |  | Q1-Q4 |  |  |  |  | Policy Briefs |
| 50 | CRA in the Oil & Gas sector with focus on IFF |  | Q1-Q4 |  |  |  |  | Integrity Plan |
| 51 | Update of NEITI data dashboard |  | Q1-Q4 |  |  |  |  | Updated Dashboard |
| Sub Total |  |  |  |  | 1 | 9 | 11 |  |
| 52 | Follow up activities on TI-CPI analysis (Monitoring Executive Order 1) |  | Q1 - Q4 |  |  |  |  | No. of reforms initiated |
| 53 | Research Studies of Anti-Corruption and Governance Survey |  | Q1 - Q4 |  |  |  |  | Survey Report |
| 54 | Follow up activities on TUGAR Ethics Survey and Gap Analysis |  | Q1 - Q4 |  |  |  |  | Gap analysis Report |
| 55 | Development of a platform for updating anti-corruption database |  | Q1 - Q4 |  |  |  |  | Platform for anti-corruption database developed |
| 56 | Implementation of the National Anti-Corruption Strategy (Monitoring and Evaluation) |  | Q1 - Q4 |  |  |  |  | NACS M&E Report |
| 57 | Corruption Risk Assessment in the Nigerian Ports - Implementation of Integrity Plan |  | Q1 - Q4 |  |  |  |  | CRA Implementation Report |
| 58 | Implementation of the Integrity Plan in the MDG Related MDAs |  | Q1 - Q4 |  |  |  |  | No. of reforms Initiatives |
| 59 | Review of Nigeria's Implementation of the UNCAC - implementation of the Remediation Plan for the 1st & 2nd review Cycles |  | Q1 - Q4 |  |  |  |  | Implementation Country report, action plan |
| 60 | Development and publication of TUGAR Policy Briefs and stakeholder engagement on the briefs |  | Q1 - Q4 |  |  |  |  | No, of policy brief developed. |
| 61 | Coordination of the Anti-Corruption Agencies on the platform of the IATT |  | Q1 - Q4 |  |  |  |  | Coordinated IATT |
| 62 | Joint Commemoration of the International Anti-Corruption Day |  | Q4 |  |  |  |  | AC day celebration report |
| 63 | Legal Retainership |  | Jan- Dec |  |  |  |  | Legal retainership signed contract |
| 64 | NSWG Sitting allowance |  | Jan- Dec |  |  |  |  | No of NSWG Sitting |
| 65 | NSWG Retreat |  | April |  |  |  |  | NSWG Retreat Hel |
| 66 | Round table meetings on compliance with covered entities |  | Jan- Dec |  |  |  |  | Minutes Of Meetings |
| 67 | E Legal Books |  | Jan - Dec |  |  |  |  | No. of books acquired. |
| 68 | Electronic Support to NSWG |  | Jan - Dec |  |  |  |  | No. of virtual meetings |
| 69 | Round Table engagements on Recommendations from Audits for Oil and Gas, Solid Minerals and FASD |  | Jun |  |  |  |  | No. of resolve Issues from the Report |
| 70 | Review of NEITI Act |  | Jan-Dec |  |  |  |  | Amended Act |
| 71 | Development Of NEITI Risk Profile |  | Jan-Dec |  |  |  |  | Risk Profile Report |
| 72 | Workshop on Internal Audit Process and procedures |  | Apr & Sept |  |  |  |  | Workshop Report |
| 73 | Dev of Procurement Manual. |  | Jan-Dec |  |  |  |  | Procurement manual |
| 74 | Procurements, Advertisement, EOI, Technical & Financial bids Evaluations. |  | Quaterly |  |  |  |  | Proc. EOIs |
| 75 | Pre-Bid Meetings |  | Mar & Jun |  |  |  |  | Report |
| Sub Total |  |  |  |  | 2 | 7 | 15 |  |
| Sub Total Objective 2 |  |  |  |  | 3 | 16 | 26 |  |
| 76 | Town hall meetings at the sub-national level in six geo-political areas of the country-States & LGA Excos, Opinion/Community leaders/NGOs/CSOs/FBOs on the NEITI/EITI processes |  | June-Nov. 2020 |  |  |  |  | Reports, attendance lists, photographs, video recordings and news reportage of the events |
| 77 | Public presentation of NEITI Reports. |  | Jan-Dec. 2021 |  |  |  |  | Report of the events, video recordings, photographs, attendance lists. |
| 78 | Engagement with - MDAs.. |  | June-Nov. 2020 |  |  |  |  | Report of the events, video recordings, photographs, attendance lists. |
| 79 | Induction Training on EITI/Natural Resource Governance for Civil Society Steering Committee (CSSC) |  | June-Nov. 2020 |  |  |  |  | Reports, attendance lists, photographs, video recordings and news reportage of the events |
| 80 | Retreat/Sensitisation workshop on natural resource governance for the Legislature |  | June -September 2021 |  |  |  |  | Media packs, attendance list, reports, news mentions and photographs. |
| 81 | Engagement with oil producing and solid minerals producing states and communities |  | March and September 2021 |  |  |  |  | Report of the events, video recordings, photographs, attendance lists. |
| 82 | Outreach to educational institutions on natural resource governance - NUC & Universities |  | June-Nov. 2021 |  |  |  |  | Report of the events, video recordings, photographs, attendance lists. |
| 83 | Engagement with Ministry of Foreign Affairs and Diplomatic Community |  | June-Nov. 2021 |  |  |  |  | Report of the events, video recordings, photographs, attendance lists. |
| 84 | Outreach to organised private sector. |  | June-Nov. 2021 |  |  |  |  | Report of the events, video recordings, photographs, attendance lists. |
| 85 | Capacity Building Workshop on EITI/NEITI Processes & Natural Resource Governance for CSOs |  | June - Nov.2021 |  |  |  |  | Recordings of the debates, Reports of the outreach programme. MoUs signed |
| 86 | Capacity Building Workshop on EITI/NEITI Processes & Natural Resource Governance for the Media |  | Jan.-June 2021 |  |  |  |  | Recordings of the debates, Reports of the outreach programme. MoUs signed |
| 87 | Capacity Building Workshop for Multi-stakeholders on the use of NEITI online IEC platforms |  | June - Nov.2021 |  |  |  |  | Report of the workshop, pictures and video recording of the event. |
| 88 | Capacity building for Communication Officers of covered entities |  | Mar-Dec. 2021 |  |  |  |  | Recordings of the debates, Reports of the outreach programme. MoUs signed |
| 89 | Media engagement & relationship managements |  | Jan-Dec 2021 |  |  |  |  | Improved Media Relationship & Management. |
| 90 | Simplification of NEITI Industry Audit reports - Oil, gas, solid minerals and FASD. |  | April - October. 2021 |  |  |  |  | Simplified report |
| 91 | Simplification and visualisation of the fiscal regimes of Nigeria's extractive sector. |  | January-April 2021 |  |  |  |  | Simplified report |
| 92 | Reprint of NEITI Publications |  | July-Dec, 2021 |  |  |  |  | NEITI Publications |
| 93 | Production of NEITI outputs-reports (statutory audit reports, policy briefs, occasional papers, quarterly reviews, and other research publications by NEITI |  | Jan-Dec. 2021 |  |  |  |  | NEITI reports published |
| 94 | Publishing the reports on the NEITI website and Presentation to the statutory recipients - OAuGF |  | June-Nov. 2021 |  |  |  |  | Reports, attendance lists, photographs, video recordings and news reportage of the events |
| 95 | Subscription renewals and management of NEITI online IEC Apps and platforms. E-Learning portal; Website; NEITI App; Online campaign adverts; etc |  | Jan-Dec.2021 |  |  |  |  | Active NEITI online platforms |
| 96 | Training of Comms Staff on communication and Digital/New media management. |  | March, 2021 |  |  |  |  | Report of the Training, pictures, and video recording of the event. |
| 97 | Design and Productions of IEC and branded materials for outreach activities |  | Jan-Dec.2021 |  |  |  |  | Number of branded items produced |
| 98 | Consumables for NEITI digital & audio-visual equipment |  | Jan-Dec. 2021 |  |  |  |  | Consumables |
| Sub Total Objective 3 |  |  |  |  | 4 | 4 | 15 |  |
| 99 | Fixed Asset Management (Financial statement conversion) |  | Q1-Q4 |  |  |  |  | Improved F/A Register |
| 100 | Compliance with financial regulations (IPSAS Conversion) - UPGRADE |  | Q1-Q4 |  |  |  |  | Improved GIFMIS Platform and ensure full compliance |
| 101 | Financial planning and cashflow management |  | Q1-Q4 |  |  |  |  | Timely and availability of fund |
| 102 | Monitoring and review of IPSAS Implementation |  | Q1-Q4 |  |  |  |  | Upgraded IPSAS |
| 103 | Vote Book Management |  | Q1-Q4 |  |  |  |  | Certified SAP staff |
| 104 | Implementing Integrated personnel payroll Information System (IPPIS) - UPGRADE |  | Q1-Q4 |  |  |  |  | Effectiveness of the software |
| 105 | Financial Reporting- Management,NSWG (Board),Donors & National Assembly |  | Q1-Q4 |  |  |  |  |  |
| 106 | Donor reporting management (Consultancy, Implementation and Training) |  | Q1-Q4 |  |  |  |  |  |
| 107 | Implementing Government Information Financial Information System (GIFMIS) -Release 2 - UPGRADE |  | Q1-Q2 |  |  |  |  |  |
| 108 | Attending to External Key Stakeholders : OAGF, MOF, MOB&N P, FIRS, FCT Inland Revenue Service (Logistics) |  | Q1-Q4 |  |  |  |  | Reports |
| 109 | Statutory Audit of NEITI Account |  | Q1-Q2 |  |  |  |  |  |
| 110 | Welfare of Staff |  | Jan-Dec 2021 |  |  |  |  | Effective and Efficient Human Capacity and Administrative Support |
| 111 | Staff Retreat |  | Q1 2021 |  |  |  |  |  |
| 112 | Training & Development |  | Jan-Dec 2021 |  |  |  |  |  |
| 113 | Performance Management |  | Jan-Dec 2021 |  |  |  |  |  |
| 114 | NYSC transport allowance |  | Jan-Dec 2021 |  |  |  |  |  |
| 115 | Office Acquisition |  |  |  |  |  |  |  |
| 116 | Rent (sqm) |  | Jan-Dec 2021 |  |  |  |  |  |
| 117 | Purchase of ACs & Electrical Fittings |  | Jan-Dec 2021 |  |  |  |  |  |
| 118 | Purchase of materials, office supplies/stationaries & furniture’s |  | Jan, May, Sept.,Dec 2021 |  |  |  |  |  |
| 119 | Payment of utility bills (Electricity, Telephone, Water, Sewage, Tenement rate) |  | Jan-Dec 2021 |  |  |  |  |  |
| 120 | Maintenance services & Safety (AC, Electricity, Plumbing, Furniture, vehicle, generator, fire extinguishers etc) |  | Jan, May, Sept.,Dec 2021 |  |  |  |  | Effective and Efficient Human Capacity and Administrative Support |
| 121 | Fuelling of generator & Pool Cars |  | Jan-Dec 2021 |  |  |  |  |  |
| 122 | Other Services (Cleaning/Fumigation & Security |  | Jan, May, Sept.,Dec 2021 |  |  |  |  |  |
| 123 | Refreshment & Meals |  | Jan-Dec 2021 |  |  |  |  |  |
| 124 | Courier Services |  | Jan, May, Sept.,Dec 2021 |  |  |  |  |  |
| 125 | Insurance |  | Jan-Dec 2021 |  |  |  |  |  |
| 126 | Local Travels |  | Jan, May, Sept.,Dec 2021 |  |  |  |  |  |
| 127 | International Travels |  | Jan-Dec 2021 |  |  |  |  |  |
| 128 | Hardware purchase |  | 2021 |  |  |  |  |  |
| 129 | Software purchase |  | 2021 |  |  |  |  |  |
| 130 | Internet bandwidth renewal/upgrade |  | 2021 |  |  |  |  |  |
| 131 | Consultancy services |  | 2021 |  |  |  |  |  |
| 132 | Subscriptions, Consumables & Others |  | 2021 |  |  |  |  |  |
| Sub Total Objective 4 |  |  |  |  | 0 | 3 | 31 |  |
| Total |  |  |  |  | 8 | 31 | 93 | 132 |
| Percentage status |  |  |  |  | 6% | 23% | 71% |  |

|  | Finance and Accounting Support |  | Q1-Q4 |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Monitoring & Evaluation Support |  | Q1-Q4 |  |  |  |  |  |
|  | Procurement Services Support |  | Q1-Q4 |  |  |  |  |  |
|  | Human Resource Mgt & capacity Building Support |  | Q1-Q4 |  |  |  |  |  |
|  | Audit and Control Support |  | Q1-Q4 |  |  |  |  |  |
|  | Legal & compliance Support |  | Q1-Q4 |  |  |  |  |  |
|  | General Administrative Support |  | Q1-Q4 |  |  |  |  |  |